## Statistics & Summary
Statistics (SABER, F62509-03-D-0002)
Yen Base Figure
| Period |  | # of | Total of | Total of | Overall | Modification |  | DO ¥ |  |  | CALT |  |  | Do not Delete
Year | From | To | DO | Award ¥ | NPI ¥ | % of NPI | # | Mod ¥ | Minimum | Maximum | Average | Minimum | Maximum | Average | Award ¥ - NPI ¥
Base | 2003-01-14 | 2004-02-27 | 48 | 1120569284 | 55109548 | 4.92% | 47 | 18904349 | 554631 | 90906615 | 22951352.8125 | 0 | 74 | 34.6458 | 1065459736
Opt 1 | 2004-02-28 | 2005-02-27 | 20 | 277119802 | 3501266 | 1.26% | 10 | -1768888 | 1242709 | 41526210 | 13944434.5 | 0 | 106 | 40.5 | 273618536
Opt 2 | 2005-02-28 | 2006-02-27 | 3 | 32662370 | 758363 | 2.32% | 0 | 0 | 10143409 | 11956923 | 10887456.6667 | 51 | 56 | 54 | 31904007
Opt 3 | 2006-02-28 | 2007-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
Ground Total |  |  | 71 | 1430351456 | 59369177 | 4.15% | 57 | 17135461 | -4357509 | 90906615 | 17425272.9259 | 0 | 106 | 36.2162 | 1370982279
Dollar Base Figure
| Period |  | # of | Total of | Total of | Overall | Modification |  | DO $ | [5 empty] | Do not Delete
Year | From | To | DO | Award $ | NPI $ | % of NPI | # | Mod $ | Minimum | Maximum | Average |  |  |  | Award $ - NPI $
Base | 2003-01-14 | 2004-02-27 | 48 | 8273541.4692 | 406892.405 | 4.92% | 47 | 139577.1932 | 4095.028 | 671194.2401 | 169457.5891 |  |  |  | 7866649.0642
Opt 1 | 2004-02-28 | 2005-02-27 | 20 | 2251874.2855 | 28383.5532 | 1.26% | 10 | -14095.8483 | 9902.8528 | 330912.503 | 113298.5067 |  |  |  | 2223490.7323
Opt 2 | 2005-02-28 | 2006-02-27 | 3 | 260278.6676 | 6043.2146 | 2.32% | 0 | 0 | 80830.4168 | 95281.879 | 86759.5559 |  |  |  | 254235.453
Opt 3 | 2006-02-28 | 2007-02-27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0
Ground Total |  |  | 71 | 10785694.4223 | 441319.1728 | 4.15% | 57 | 125481.3449 | -34723.9541 | 671194.2401 | 131433.546 |  |  |  | 10344375.2495
Do not Delete
[15 empty] | Year | <$25,000 | >=$25,000
[15 empty] | Base | 7 | 41
[15 empty] | Opt 1 | 4 | 16
[15 empty] | Opt 2 | 0 | 3
[15 empty] | Opt 3 | 0 | 0
[15 empty] | Total | 11 | 60
N/A after 28 Feb 05
Progress Chart
Statistics & Summary
Return to DO Tracker
PB Tracker

## DO Tracker
|  | DO Tracker (SABER, F62509-03-D-0002) | [6 empty] | Legend | (Color automatically changes) |  |  | < Current Status >
|  | Current PB Coverage: |  |  |  |  | 300000000 | 100% | [25 empty] | Preparing
|  | Total # of Active DOs: |  |  |  |  | 6 | [26 empty] | Done
|  | Total Amount of Active DOs: |  |  |  |  | 110513136 | 36.84% |  |  |  |  | Summary by Filter Button Selection | [14 empty] | Post-Completion Admin. | [5 empty] | See DO
|  | Extra Bonding: |  |  |  |  | 189486864 | 63.16% |  |  |  |  | 1430351456 | 10785694.4223 | 59369177 | 441319.1728 | 4.15% | 135 |  |  |  |  | Progress % |  |  |  | 33.131 | Warranty |  | Final Payment |  | Close-Out
|  |  |  | QKKA | DO | MOD | TITLE |  |  | CURRENCYRATE |  | GOVCOSTESTIMATE | AWARDYEN | AWARDAMOUNT | [5 empty] | NTPDATE | COMPLETIONDATE | ACCEPTANCE |  |  | REMARKS
Fuel-Hachi
HAS
Main Base
Ripsaw
Sec Hill
Ser# | Active | FY | YR | QKKA | DO# | Mod | Title | BLDG | Location | ¥ Rate | AF 9 (¥) | GCE (¥) | Award (¥) | Award ($) | NPI (¥) | NPI ($) | NPI % | PR Date | Awd Date | NTP | CompDate | Final Date | Schedule | Actual | Latest Status or Reason for Modification | B/S | CALT | Warranty | Warranty | Voucher # | Date Paid | Final Accept | Close-Out | Closed
[9 empty] | Main Base | [17 empty] | / 60 | Period | Repair |  |  | Notice Date | Due | out
|  | 3 | B | 03-1040 | 5000 | N/A | Const Porch/Overhang | 926 | Main Base | 135.4401 | 8250000 | 8150000 | 8221240 | 60700.1914 | 77040 | 568.8123 | 0.94% | 2003-02-04 | 2003-04-03 | 2003-04-07 | 2003-08-04 | 2003-07-11 | 100% | 100% | Completed | v2u | 58 | Expired |  | 3HYXTAI | 2003-08-14 | 2003-07-21 | 2004-01-17 | Done | NAVY O/M
|  | 3 | B | 03-1060 | 5001 | N/A | Rnv Building | 958 | Main Base | 135.4401 | 8058680 | 6650000 | 6754687 | 49872.1354 | 291040 | 2148.8466 | 4.31% | 2003-01-31 | 2003-03-27 | 2003-03-27 | 2003-05-20 | 2003-05-13 | 100% | 100% | Completed | v2u | 55 | Expired |  | DX30013204 | 2003-06-27 | 2003-05-20 | 2003-11-16 | Done
|  | 3 | B | 03-1184 | 5002 | N/A | PFRM Refinish Courts & Hall | 622 | Main Base | 135.4401 | 3386000 | 3000000 | 3188160 | 23539.262 | 376640 | 2780.8603 | 11.81% | 2003-03-05 | 2003-03-28 | 2003-03-31 | 2003-05-09 | 2003-04-23 | 100% | 100% | Completed | b3h | 23 | Expired |  | DX30011755 | 2003-05-27 | 2003-04-24 | 2003-10-21 | Done
|  | 3 | B | 03-1184 | 5002 | 1 | PFRM Refinish Courts & Hall | 622 | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-04-07 | N/A | N/A | 2003-04-23 | N/A | N/A | Admin Mod for error correction | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 02-1067 | 5003 | N/A | Paint Floor | 909 | Main Base | 135.4401 | 7042880 | 6700000 | 6601584 | 48741.7242 | 211860 | 1564.2339 | 3.21% | 2003-02-18 | 2003-03-27 | 2003-04-07 | 2003-06-23 | 2003-05-30 | 100% | 100% | Completed | v2u | 37 | Expired |  | DX30013324 | 2003-07-01 | 2003-05-30 | 2003-11-26 | Done
|  | 3 | B | 03-5007 | 5004 | N/A | Rnv Pasta La Vista - Proshop | 1464 | Main Base | 135.4401 | 74492000 | 12650000 | 14337206 | 105856.434 | 492200 | 3634.0788 | 3.43% | 2003-02-18 | 2003-04-01 | 2003-04-01 | 2003-05-29 | 2003-05-09 | 100% | 100% | Completed | v2u | 42 | Expired |  | DX30013205 | 2003-06-27 | 2003-05-21 | 2003-11-17 | Done
|  | 3 | B | 03-5007 | 5004 | 1 | Rnv Pasta La Vista - Proshop | 1464 | Main Base | 135.4401 | 0 | -1281 | -1281 | -9.4581 | -77040 | -568.8123 |  | N/A | 2003-04-09 | N/A | N/A | 2003-05-09 | N/A | N/A | Mod to additional and deletion work | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO | GFP
|  | 3 | B | 03-1183 | 5005 | N/A | Inst Catch Bars | 302 | Main Base | 135.4401 | 1896160 | 1895000 | 1886889 | 13931.5387 | 173340 | 1279.8278 | 9.19% | 2003-02-24 | 2003-04-03 | 2003-04-14 | 2003-06-02 | 2003-05-21 | 100% | 100% | Completed | v2u | 38 | Expired | 2003-05-30 | DX30012948 | 2003-06-20 | 2003-05-21 | 2003-11-17 | Done
|  | 3 | B | 03-1068 | 5006 | N/A | Inst Two Lights, D-37 | 3206 | HAS | 135.4401 | 1083520 | 950000 | 998500 | 7372.2627 | 19260 | 142.2031 | 2% | 2003-03-05 | 2003-04-03 | 2003-04-14 | 2003-06-12 | 2003-05-01 | 100% | 100% | Completed | b3h | 29 | Expired |  | DX30011989 | 2003-06-02 | 2003-05-01 | 2003-10-28 | Done
|  | 3 | B | 03-1039 | 5007 | N/A | Replace Water Sample | 1359 | Main Base | 135.4401 | 21331800 | 19740000 | 20821107 | 153729.2648 | 464380 | 3428.6744 | 2.23% | 2003-03-05 | 2003-04-18 | 2003-04-21 | 2003-09-17 | 2003-09-04 | 100% | 100% | Completed | v2u | 44 | Expired |  | DW40001403 | 2003-11-04 | 2003-10-06 | 2004-04-03 | Done
|  | 3 | B | 03-1039 | 5007 | 2 | Replace Water Sample | 1359 | Main Base | 135.4401 | 2911960 | 2750000 | 2886508 | 21312.0634 | 433350 | 3199.5694 |  | 2003-08-27 | 2003-08-29 | N/A | N/A | 2003-09-04 | N/A | N/A | Mod for additional work by DSC | v2u | 2 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1039 | 5007 | 1 | Replace Water Sample | 1359 | Main Base | 135.4401 | 0 | -317561 | -317561 | -2344.6601 | 0 | 0 |  | N/A | 2003-04-23 | N/A | N/A | 2003-09-04 | N/A | N/A | Mod to remove compressor by Addm No.1 | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1169 | 5008 | N/A | Rpr Heating System | 1500 | Sec Hill | 135.4401 | 3792320 | 3750000 | 3783610 | 27935.6705 | 0 | 0 |  | 2003-03-06 | 2003-05-02 | 2003-05-06 | 2003-08-13 | 2003-08-07 | 100% | 100% | Completed | b3h | 57 | Expired |  | DX30017312 | 2003-09-12 | 2003-08-20 | 2004-02-16 | Done
|  | 3 | B | 02-1030 | 5009 | N/A | Rpr Sewer Line, North Friendshp | Road | Main Base | 135.4401 | 51467200 | 47000000 | 48792291 | 360249.9629 | 481500 | 3555.0771 | 0.99% | 2003-03-31 | 2003-05-02 | 2003-05-06 | 2003-11-03 | 2003-11-12 | 100% | 100% | Completed | v2u | 32 | Expired |  | DW40004443 | 2004-01-08 | 2003-12-11 | 2004-06-08 | Done
|  | 3 | B | 02-1030 | 5009 | 1 | Rpr Sewer Line, North Friendshp | Road | Main Base | 135.4401 | 0 | -300000 | -120840 | -892.2025 | -48150 | -355.5077 |  | N/A | 2003-09-25 | N/A | 2003-11-21 | 2003-11-12 | 100% | 100% | Mod to offset DSC cost by Addm No.1 | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1065 | 5010 | N/A | Rpr&Rpnt Ceiling Tiles, Potter Anx | 622 | Main Base | 135.4401 | 5688480 | 5113800 | 5551713 | 40990.172 | 0 | 0 | 0% | 2003-04-14 | 2003-05-28 | 2003-06-23 | 2003-09-05 | 2003-07-24 | See Mod01 | See Mod01 | Completed | b3h | 44 | Expired |  | DX30017176 | 2003-09-10 | 2003-08-19 | 2004-02-15 | Done
|  | 3 | B | 03-1065 | 5010 | 1 | Rpr&Rpnt Ceiling Tiles, Potter Anx | 622 | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-06-16 | 2003-06-16 | 2003-08-29 | 2003-07-24 | 100% | 100% | Mod to change PP | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 44-4867 | 5011 | N/A | Repaint Floor | 3007 | HAS | 135.4401 | 30137250 | 30087250 | 30106297 | 222284.9584 | 85600 | 632.0137 | 0.28% | 2003-04-08 | 2003-06-04 | 2003-06-24 | 2003-10-21 | 2003-09-22 | 100% | 100% | Completed | b3h | 57 | Expired |  | DW40000695 | 2003-10-17 | 2003-09-23 | 2004-03-21 | Done
|  | 3 | B | 03-1052B | 5012 | N/A | Modify Bldg. 3264 SCIF | 3264 | HAS | 135.4401 | 5755580 | 5600000 | 5755580 | 42495.391 | 287563 | 2123.1747 | 5% | 2003-04-14 | 2003-06-04 | 2003-06-04 | 2003-09-02 | 2003-09-10 | 100% | 100% | Completed | v2u | 51 | Expired |  | DW40001740 | 2003-11-12 | 2003-10-16 | 2004-04-13 | Done
|  | 3 | B | 03-1052B | 5012 | 1 | Modify Bldg. 3264 SCIF | 3264 | HAS | 135.4401 | 1410000 | 1280000 | 1247205 | 9208.5357 | 0 | 0 |  | 2003-08-28 | 2003-08-28 | N/A | 2003-09-22 | 2003-09-10 | N/A | N/A | Completed | v2u | 0 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1044 | 5013 | N/A | Rpr Septic Tank | 40 | Ripsaw | 135.4401 | 25056400 | 21400000 | 21736968 | 160491.3759 | 2387384 | 17626.8624 | 10.98% | 2003-04-08 | 2003-06-06 | 2003-06-23 | 2003-10-20 | 2003-10-17 | 100% | 100% | Completed | v2u | 59 | Expired |  | DW40003272 | 2003-12-11 | 2003-11-14 | 2004-05-12 | Done
|  | 3 | B | 03-1069 | 5014 | N/A | Inst Security Fence, B/3122 | 3122 | HAS | 135.4401 | 1557560 | 1557560 | 6303874 | 46543.6307 | 234865 | 1734.0876 | 3.73% | 2003-04-22 | 2003-06-17 | 2003-06-17 | 2003-09-15 | 2003-07-25 | 100% | 100% | Completed | b3h | 56 | Expired |  | DX30017177 | 2003-09-10 | 2003-08-19 | 2004-02-15 | Done
|  | 3 | B | 13-5857 | 5015 | N/A | Inst Force Protection Cable | Gates | Main Base | 135.4401 | 16930000 | 4700000 | 4828528 | 35650.6529 | 0 | 0 | 0% | 2003-04-14 | 2003-06-12 | 2003-06-23 | 2003-09-05 | 2003-09-04 | 100% | 100% | Completed | b3h | 59 | Expired |  | DW40002183 | 2003-11-21 | 2003-10-08 | 2004-04-05 | Done
|  | 3 | B | 13-5857 | 5015 | 2 | Inst Force Protection Cable | Gates | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-11 | N/A | N/A | 2003-09-04 | N/A | N/A | Admin Mod to change acct data | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 13-5857 | 5015 | 1 | Inst Force Protection Cable | Gates | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-07-18 | N/A | N/A | 2003-09-04 | 100% | 100% | Mod to change work condition - No cost | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-5007A | 5016 | N/A | Pnv Club House Dining Area | 1464 | Main Base | 135.4401 | 60154727 | 55700000 | 59572139 | 439841.2213 | 772968 | 5707.0838 | 1.3% | 2003-04-21 | 2003-06-16 | 2003-06-16 | 2003-10-14 | 2003-12-12 | See Mod01 | See Mod01 | Completed | v2u | 56 | Expired |  | DW40004669 | 2004-01-15 | 2003-12-19 | 2004-06-16 | Done
|  | 3 | B | 03-5007A | 5016 | 1 | Pnv Club House Dining Area | 1464 | Main Base | 135.4401 | 5451460 | 4930000 | 5324227 | 39310.5661 | 630230 | 4653.2009 |  | 2003-09-10 | 2003-09-25 | N/A | 2003-12-12 | 2003-12-12 | 100% | 100% | Mod to incorporate Addendum No. 1 | v2u | 15 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1192B | 5017 | N/A | Rnv 14 FS | 3120 | HAS | 135.4401 | 10293448 | 9300000 | 16684948 | 123190.606 | 1337500 | 9875.2142 | 8.02% | 2003-04-21 | 2003-06-20 | 2003-06-25 | 2003-10-22 | 2003-12-02 | See Mod01 | See Mod01 | Completed | v2u | 60 | Expired |  | DW40004670 | 2004-01-15 | 2003-12-17 | 2004-06-14 | Done
|  | 3 | B | 03-1192B | 5017 | 1 | Rnv 14 FS | 3120 | HAS | 135.4401 | 3501124 | 3100000 | 2860828 | 21122.4593 | 154080 | 1137.6247 |  | 2003-09-12 | 2003-09-24 | N/A | 2003-12-08 | 2003-12-02 | 100% | 100% | Mod to add P-tile in 1st Hallway | v2u | 12 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 97-1048 | 5018 | N/A | Rpr Base Supply | 1334 | Main Base | 135.4401 | 36568800 | 32500000 | 31976784 | 236095.3957 | 53500 | 395.0086 | 0.17% | 2003-04-21 | 2003-06-20 | 2003-07-14 | 2003-11-10 | 2003-10-30 | 100% | 100% | Completed | v2u | 60 | Expired |  | DW40002947 | 2003-12-05 | 2003-11-04 | 2004-05-02 | Done
|  | 3 | B | 01-0007 | 5019 | N/A | Const LOX Cart Storage | A-14 | HAS | 135.4401 | 44695200 | 24000000 | 22955537 | 169488.4824 | 0 | 0 | 0% | 2003-04-22 | 2003-06-20 | 2003-07-07 | 2003-10-14 | 2003-10-30 | See Mod01 | See Mod01 | Completed | v2u | 59 | Expired |  | DW40003802 | 2003-12-22 | 2003-11-24 | 2004-05-22 | Done
|  | 3 | B | 01-0007 | 5019 | 1 | Const LOX Cart Storage | A-14 | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2003-04-22 | 2003-06-20 | 2003-07-07 | 2003-11-13 | 2003-10-30 | 100% | 100% | Mod to extend PP per Govt cause of delay | v2u | 59 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1041 | 5020 | N/A | Inst Security Meas. | 3263 | HAS | 135.4401 | 13950320 | 10900000 | 10687433 | 78908.9273 |  | 0 | 0% | 2003-04-28 | 2003-06-23 | 2003-07-07 | 2003-11-03 | 2003-11-21 | See Mod01 | See Mod01 | Completed | v2u | 56 | Expired |  | DW40004671 | 2004-01-15 | 2003-12-19 | 2004-06-16 | Done
|  | 3 | B | 03-1041 | 5020 | 1 | Inst Security Meas. | 3263 | HAS | 135.4401 | 0 | 0 | 0 | 0 |  | 0 |  | N/A | 2003-10-21 | N/A | 2003-11-21 | 2003-11-21 | 100% | 100% | Mod to extend PP per Govt cause of delay | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 13-5857B | 5021 | N/A | Inst Force Protection Cable | Gates | Main Base | 135.4401 | 12054168 | 11500000 | 10047296 | 74182.5796 | 0 | 0 | 0% | 2003-06-17 | 2003-06-30 | 2003-07-14 | 2003-10-11 | 2003-11-06 | See Mod02 | See Mod02 | Completed | b3h | 13 | Expired |  | DW40004383 | 2004-01-07 | 2003-12-05 | 2004-06-02 | Done
|  | 3 | B | 13-5857B | 5021 | 2 | Inst Force Protection Cable | Gates | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-11 | N/A | N/A | 2003-11-06 | N/A | N/A | Admin Mod to change acct data | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 13-5857B | 5021 | 1 | Inst Force Protection Cable | Gates | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-03 | 2003-07-14 | 2004-05-01 | 2003-11-06 | 100% | 100% | Mod to extend performance period | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1192A | 5022 | N/A | Rnv 13FS | 3267 | HAS | 135.4401 | 35214426 | 34400000 | 35063415 | 258885.0348 | 2050120 | 15136.7283 | 5.85% | 2003-06-30 | 2003-07-03 | 2003-07-16 | 2004-01-12 | 2004-03-30 | See Mod01 | See Mod01 | Completed | v2u | 3 | Expired |  | DW40011385 | 2004-05-06 | 2004-04-05 | 2004-10-02 | Done
|  | 3 | B | 03-1192A | 5022 | 1 | Rnv 13FS | 3267 | HAS | 135.4401 | 338600.25 | 240000 | 270009 | 1993.5676 | 0 | 0 |  | 2003-08-22 | 2003-08-26 | 2003-07-16 | 2004-02-11 | 2004-03-30 | See Mod02 | See Mod02 | Mod for change color order | v2u | 4 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1192A | 5022 | 2 | Rnv 13FS | 3267 | HAS | 135.4401 | 0 | -629680 | -730876 | -5396.3043 | 0 | 0 |  | N/A | 2004-02-10 | N/A | 2004-04-01 | 2004-03-30 | 100% | 100% | Mod to delete P-Tile and add Light in Vault Area | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 83-5850B | 5023 | N/A | Const Wall, Independence Dr Ph-2 | Housing | Main Base | 135.4401 | 28442400 | 27546375 | 28415428 | 209800.7016 | 1916905 | 14153.157 | 6.75% | 2003-07-22 | 2003-07-25 | 2003-08-07 | 2004-05-05 | 2003-11-12 | 100% | 100% | Completed | b3h | 3 | Expired |  | DW40003710 | 2003-12-18 | 2003-11-13 | 2004-05-11 | Done
|  | 3 | B | 83-5850B | 5023 | 1 | Const Wall, Independence Dr Ph-2 | Housing | Main Base | 135.4401 | 0 | -14050000 | -13215584 | -97575.1199 | -1055020 | -7789.569 |  | N/A | 2003-09-16 | N/A | N/A | 2003-11-12 | 100% | 100% | Mod to decrease wall length by Addm No.1 | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 83-5850B | 5023 | 2 | Const Wall, Independence Dr Ph-2 | Housing | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-29 | N/A | N/A | 2003-11-12 | N/A | N/A | Admin Mod to change acct data | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1140 | 5024 | N/A | Rpr Perimeter Fence Sec Hill, North | Sec Hill | Sec Hill | 135.4401 | 92099200 | 86000000 | 90906615 | 671194.2401 | 12018240 | 88734.7248 | 13.22% | 2003-07-22 | 2003-07-25 | 2003-09-09 | 2004-08-06 | 2004-06-30 | See Mod01 | See Mod01 | Completed | v2u | 3 | Expired |  | DW40017755 | 2004-08-11 | 2004-07-15 | 2005-01-11 | Done
|  | 3 | B | 03-1140 | 5024 | 1 | Rpr Perimeter Fence Sec Hill, North | Sec Hill | Sec Hill | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-11 | N/A | N/A | 2004-06-30 | N/A | N/A | Admin Mod to change acct data | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1140 | 5024 | 2 | Rpr Perimeter Fence Sec Hill, North | Sec Hill | Sec Hill | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-11-14 | N/A | 2004-07-01 | 2004-06-30 | 100% | 100% | Completed | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1140B | 5025 | N/A | Rpr Perimeter Fence Sec Hill, West | Sec Hill | Sec Hill | 135.4401 | 81264000 |  | 86892325 | 641555.3813 | 11363400 | 83899.8199 | 13.08% | 2003-07-22 | 2003-07-25 | 2003-09-09 | 2004-08-06 | 2004-02-17 | See Mod01 | See Mod01 | Completed | v2u | 3 | Expired |  | DW40014535 | 2004-06-28 | 2004-06-02 | 2004-11-29 | Done
|  | 3 | B | 03-1140B | 5025 | 1 | Rpr Perimeter Fence Sec Hill, West | Sec Hill | Sec Hill | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-11 | N/A | N/A | 2004-02-17 | N/A | N/A | Admin Mod to change acct data | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1140B | 5025 | 2 | Rpr Perimeter Fence Sec Hill, West | Sec Hill | Sec Hill | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-11-14 | N/A | 2004-03-08 | 2004-02-17 | 100% | 100% | Mod to remove Exclusion Period | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1140C | 5026 | N/A | Rpr Perimeter Fence Sec Hill, South | Sec Hill | Sec Hill | 135.4401 | 78555200 |  | 76634236 | 565816.4458 | 10515960 | 77642.8842 | 13.72% | 2003-07-22 | 2003-07-25 | 2003-09-09 | 2004-08-06 | 2004-05-13 | See Mod01 | See Mod01 | Completed | v2u | 3 | Expired |  | DW40013165 | 2004-06-02 | 2004-04-29 | 2004-10-26 | Done
|  | 3 | B | 03-1140C | 5026 | 1 | Rpr Perimeter Fence Sec Hill, South | Sec Hill | Sec Hill | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-11 | N/A | N/A | 2004-04-16 | N/A | N/A | Admin Mod to change acct data | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1140C | 5026 | 2 | Rpr Perimeter Fence Sec Hill, South | Sec Hill | Sec Hill | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-11-14 | N/A | N/A | 2004-04-16 | N/A | N/A | Mod to change Exclusion Period | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1140C | 5026 | 3 | Rpr Perimeter Fence Sec Hill, South | Sec Hill | Sec Hill | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-01-28 | N/A | 2004-04-19 | 2004-04-16 | 100% | 100% | Mod to change Exclusion Period | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1511 | 5027 | N/A | Rpr Perimeter Fence Sec Hill, Main Base | Misc. | Main Base | 135.4401 | 48893840 |  | 37365622 | 275883.0066 | 2542320 | 18770.8072 | 6.8% | 2003-07-22 | 2003-07-25 | 2003-09-09 | 2004-08-06 | 2004-03-08 | See Mod01 | See Mod01 | Completed | v2u | 3 | Expired |  | DW40013867 | 2004-06-14 | 2004-05-19 | 2004-11-15 | Done
|  | 3 | B | 03-1511 | 5027 | 1 | Rpr Perimeter Fence Sec Hill, Main Base | Misc. | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-11-14 | N/A | 2004-03-08 | 2004-03-08 | 100% | 100% | Mod to remove Exclusion Period | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1512 | 5028 | N/A | Repl Lighting Sys. HAS Ph-1 | HAS | HAS | 135.4401 | 36568800 | 34880000 | 35228647 | 260104.9984 | 0 | 0 | 0% | 2003-07-22 | 2003-07-25 | 2003-10-06 | 2004-03-15 | 2004-08-12 | See Mod01 | See Mod01 | Completed | v2u | 3 | Expired |  | DW40020171 | 2004-09-14 | 2004-08-24 | 2005-02-20 | Done | GFP
|  | 3 | B | 03-1512 | 5028 | 1 | Repl Lighting Sys. HAS Ph-1 | HAS | HAS | 135.4401 | 17533669 | 18400000 | 17533643 | 129456.8078 | 1540800 | 11376.2468 |  | 2003-09-30 | 2003-09-30 | N/A | N/A | 2004-08-12 | N/A | N/A | Mod to add Task Lightings | v2u | 0 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1512 | 5028 | 3 | Repl Lighting Sys. HAS Ph-1 | HAS | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-02-26 | N/A | 2004-12-08 | 2004-08-12 | 100% | 100% | Mod to extend PP per Govt cause of delay | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1196 | 5029 | N/A | Renovate Falcon Feeder | 3262 | HAS | 135.4401 | 27766000 | 27720000 | 26771061 | 197659.7847 | 1021850 | 7544.6637 | 3.82% | 2003-06-12 | 2003-08-08 | 2003-08-18 | 2003-12-15 | 2003-12-24 | See Mod01 | See Mod01 | Completed | b3h | 57 | Expired |  | DW40006099 | 2004-02-17 | 2004-01-22 | 2004-07-20 | Done
|  | 3 | B | 03-1196 | 5029 | 1 | Renovate Falcon Feeder | 3262 | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-12-02 | N/A | 2003-12-26 | 2003-12-24 | 100% | 100% | Completed | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-8007 | 5030 | N/A | Inst Security Meas. Hospital | 99 | Main Base | 135.4401 | 9142207 | 8450000 | 8761002 | 64685.4366 | 0 | 0 | 0% | 2003-07-03 | 2003-09-15 | 2003-09-15 | 2004-06-14 | 2004-07-20 | N/A | N/A | Completed | v2u | 74 | Expired |  | DW40020056 | 2004-09-13 | 2004-08-24 | 2005-02-20 | Done
|  | 3 | B | 03-8007 | 5030 | 1 | Inst Security Meas. Hospital | 99 | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-17 | N/A | N/A | 2004-07-20 | N/A | N/A | Admin Mod to change acct data | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-8007 | 5030 | 2 | Inst Security Meas. Hospital | 99 | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-07-12 | N/A | 2004-07-21 | 2004-07-20 | 100% | 100% | Completed | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 31-6456 | 5031 | N/A | Repair Concrete Floor Slub | HAS | HAS | 135.4401 | ¥15,981,920 | ¥3,150,000 | 3419826 | 25249.73 | ¥0 | 0 | 0% | 2003-07-11 | 2003-09-08 | 2003-10-06 | 2004-03-03 | 2004-03-30 | See Mod01 | See Mod01 | Completed | v2u | 59 | Expired |  | DW40011386 | 2004-05-06 | 2004-04-05 | 2004-10-02 | Done
|  | 3 | B | 31-6456 | 5031 | 1 | Repair Concrete Floor Slub | HAS | HAS | 135.4401 | 162528 | 162528 | 156386 | 1154.6507 | 0 | 0 |  | 2003-09-15 | 2003-09-19 | N/A | N/A | 2004-03-30 | N/A | N/A | Mod for additional HAS | v2u | 4 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 31-6456 | 5031 | 2 | Repair Concrete Floor Slub | HAS | HAS | 135.4401 | 162528 | 162528 | 156386 | 1154.6507 | 0 | 0 |  | 2004-02-04 | 2004-02-10 | N/A | 2004-04-19 | 2004-03-30 | 100% | 100% | Mod for additional HAS | v2u | 6 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1191 | 5032 | N/A | Repl Lighting, B/909 | 909 | Main Base | 135.4401 | 2708800 | 2980000 | 2790425 | 20602.6502 | 0 | 0 | 0% | 2003-07-24 | 2003-09-18 | 2003-09-22 | 2003-11-05 | 2003-11-21 | See Mod01 | See Mod01 | Completed | b3h | 56 | Expired |  | DW40004346 | 2004-01-06 | 2003-11-28 | 2004-05-26 | Done | GFP
|  | 3 | B | 03-1191 | 5032 | 1 | Repl Lighting, B/909 | 909 | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-10-23 | N/A | 2003-12-05 | 2003-11-21 | 100% | 100% | Mod to extend PP per Govt cause of delay | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1189 | 5033 | N/A | Repl Lighting, B/3007 | 3007 | HAS | 135.4401 | 2708800 | 1250000 | 1219478 | 9003.8179 | 0 | 0 | 0% | 2003-07-24 | 2003-09-18 | 2003-09-22 | 2003-11-05 | 2003-10-08 | 100% | 100% | Completed | b3h | 56 | Expired |  | DW40001829 | 2003-11-13 | 2003-10-20 | 2004-04-17 | Done | GFP
|  | 3 | B | 03-1190 | 5034 | N/A | Repl Lighting, B/3270 | 3270 | HAS | 135.4401 | 2708800 | 540000 | 554631 | 4095.028 | 0 | 0 | 0% | 2003-07-25 | 2003-09-18 | 2003-09-22 | 2003-10-20 | 2003-10-30 | See Mod01 | See Mod01 | Completed | b3h | 55 | Expired |  | DW40002290 | 2003-11-25 | 2003-11-03 | 2004-05-01 | Done | GFP
|  | 3 | B | 03-1190 | 5034 | 1 | Repl Lighting, B/3270 | 3270 | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-10-14 | N/A | 2003-11-20 | 2003-10-30 | 100% | 100% | Mod to extend PP per Govt cause of delay | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1193 | 5035 | N/A | Rnv Mokuteki Community Center Ph1 | 626 | Main Base | 135.4401 | 23702000 | 23300000 | 23047922 | 170170.592 | 172270 | 1271.9276 | 0.75% | 2003-08-25 | 2003-09-19 | 2003-09-22 | 2004-07-20 | 2004-07-20 | 100% | 100% | Completed | v2u | 25 | Expired |  | DW40019730 | 2004-09-08 | 2004-08-11 | 2005-02-07 | Done
|  | 3 | B | 03-8015 | 5036 | N/A | Rnv Operating Area, B/99 | 99 | Main Base | 135.4401 | 5417600 | 1650000 | 1530717 | 11301.8006 | 173340 | 1279.8278 | 11.32% | 2003-07-24 | 2003-09-19 | 2003-10-06 | 2003-12-04 | 2003-12-24 | 100% | 100% | Completed | v2u | 57 | Expired |  | DW40005678 | 2004-02-09 | 2004-01-08 | 2004-07-06 | Done
|  | 3 | B | 02-4002 | 5037 | N/A | Rpr Sewer Line, Main Housing Area | Housing | Main Base | 135.4401 | 15575611 | 4800000 | 5444629 | 40199.5347 | 0 | 0 | 0% | 2003-09-19 | 2003-09-19 | 2003-10-20 | #VALUE! | 2004-07-13 | 100% | 100% | Completed | v2u | 0 | Expired |  | DW40018245 | 2004-08-20 | 2004-07-27 | 2005-01-23 | Done
|  | 3 | B | 02-4002 | 5037 | 1 | Rpr Sewer Line, Main Housing Area | Housing | Main Base | 135.4401 | 0 | 0 | -4060 | -29.9764 | 0 | 0 | -0% | N/A | 2004-05-07 | N/A | 2004-09-16 | 2004-07-13 | N/A | N/A | Mod to resolve DSC | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 04-1035 | 5038 | N/A | Const Overhang, AGE Storage | 3270 | HAS | 135.4401 | 97516872 | 70278400 | 69446362 | 512745.9445 | 0 | 0 | 0% | 2003-09-20 | 2003-09-20 | 2003-09-29 | #VALUE! | 2004-07-29 | See Mod01 | See Mod01 | Completed | v2u | 0 | Expired |  | DW40019731 | 2004-09-08 | 2004-08-11 | 2005-02-07 | Done
|  | 3 | B | 04-1035 | 5038 | 1 | Const Overhang, AGE Storage | 3270 | HAS | 135.4401 | 5417604 | 3255000 | 3010494 | 22227.4939 | 0 | 0 |  | 2003-09-23 | 2003-09-24 | N/A | #VALUE! | 2004-07-29 | 100% | 100% | Mod to add lighting fixture | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 04-1035 | 5038 | 2 | Const Overhang, AGE Storage | 3270 | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-09-27 | N/A | N/A | 2004-07-29 | N/A | N/A | Admin Mod to change acct data | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 04-1035 | 5038 | 3 | Const Overhang, AGE Storage | 3270 | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-04-19 | N/A | 2004-08-02 | 2004-07-29 | N/A | N/A | Mod to shorten the exclusion priod. | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 00-8017 | 5039 | N/A | Rpr Cracks & Paint Tunnel | 99 | Main Base | 135.4401 | 22483040 | 20800000 | 22042357 | 162746.166 | 0 | 0 | 0% | 2003-07-31 | 2003-09-25 | 2003-10-27 | #VALUE! | 2004-08-10 | 100% | 100% | Completed | v2u | 56 | Expired |  | DW40020172 | 2004-09-14 | 2004-08-25 | 2005-02-21 | Done
|  | 3 | B | 03-8012 | 5040 | N/A | Inst Revolving Doors, Main Ent. | 99 | Main Base | 135.4401 | 24108320 | 15560000 | 16179627 | 119459.6504 | 53500 | 395.0086 | 0.33% | 2003-07-31 | 2003-09-25 | 2003-10-06 | 2004-08-04 | 2004-08-03 | 100% | 100% | Completed | v2u | 56 | Expired |  | DW40019732 | 2004-09-08 | 2004-08-11 | 2005-02-07 | Done
|  | 3 | B | 03-1517 | 5041 | N/A | Rnv SABER Office | 1078 | Main Base | 135.4401 | 9480807 | 9400000 | 9430386 | 69627.7247 | 110210 | 813.7177 | 1.17% | 2003-09-23 | 2003-09-29 | 2003-10-06 | 2004-01-05 | 2004-06-09 | See Mod01 | See Mod01 | Completed | b3h | 6 | Expired |  | DW40015426 | 2004-07-07 | 2004-06-09 | 2004-12-06 | Done
|  | 3 | B | 03-1517 | 5041 | 1 | Rnv SABER Office | 1078 | Main Base | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2003-12-02 | N/A | 2004-02-14 | 2004-06-09 | See Mod02 | See Mod02 | Mod to extend PP per Govt cause of delay | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1517 | 5041 | 2 | Rnv SABER Office | 1078 | Main Base | 135.4401 | 0 | -1108526 | -1108526 | -8184.6218 | 0 | 0 | -0% | N/A | 2004-06-09 | N/A | 2004-06-09 | 2004-06-09 | 100% | 100% | T4C | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1518 | 5042 | N/A | Rnv CEC Office | 1080 | Main Base | 135.4401 | 10158007 | 8584999 | 6636004 | 48995.8587 | 372895 | 2753.2097 | 5.62% | 2003-09-23 | 2003-09-29 | 2003-10-06 | 2003-12-04 | 2003-12-04 | 100% | 100% | Completed | b3h | 6 | Expired |  | DW40007164 | 2004-03-10 | 2004-02-13 | 2004-08-11 | Done
|  | 3 | B | 02-1133 | 5043 | N/A | Inst Bypass Gate, HAS Area ECP | HAS | HAS | 135.4401 | 19146407 | 20561100 | 19146407 | 141364.3891 | 15408 | 113.7625 | 0.08% | 2003-09-27 | 2003-09-27 | 2003-10-06 | #VALUE! | 2004-08-04 | N/A | N/A | Completed | v2u | 0 | Expired |  | DW40020057 | 2004-09-13 | 2004-08-24 | 2005-02-20 | Done
|  | 3 | B | 02-1133 | 5043 | 1 | Inst Bypass Gate, HAS Area ECP | HAS | HAS | 135.4401 | 0 | -1000 | -96 | -0.7088 | 0 | 0 | -0% | N/A | 2004-06-17 | N/A | 2004-08-30 | 2004-08-04 | 100% | 100% | Mod for Addl Conduits/Heater Del Pave area etc | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-5009 | 5044 | N/A | Rnv Longhorn Lounge | 485 | Main Base | 135.4401 | 13544000 | 12420000 | 13378413 | 98777.3414 | 184040 | 1358.8295 | 1.38% | 2003-08-26 | 2003-09-29 | 2003-10-06 | 2003-12-19 | 2004-01-30 | See Mod01 | See Mod01 | Completed | v2u | 34 | Expired |  | 27030 | 2004-03-18 | 2004-02-10 | 2004-08-08 | Done | NAFI-35SVS
|  | 3 | B | 03-5009 | 5044 | 1 | Rnv Longhorn Lounge | 485 | Main Base | 135.4401 | 1000000 | 985000 | 957487 | 7069.4499 | 0 | 0 |  | 2003-12-17 | 2003-12-18 | N/A | 2004-01-30 | 2004-01-30 | 100% | 100% | Mod to change wall paint to wall covering | v2u | 1 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1513 | 5045 | N/A | Repl Lighting Sys. HAS Ph-2 | HAS | HAS | 135.4401 | 44151791 | 44240000 | 44151791 | 325987.5842 | 770400 | 5688.1234 | 1.74% | 2003-09-30 | 2003-09-30 | 2003-10-06 | 2004-03-15 | 2004-09-14 | See Mod01 | See Mod01 | Completed | v2u | 0 | Expired |  | DX50000842 | 2004-10-15 | 2004-09-17 | 2005-03-16 |  | GFP
|  | 3 | B | 03-1513 | 5045 | 1 | Repl Lighting Sys. HAS Ph-2 | HAS | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-02-26 | N/A | 2004-12-08 | 2004-09-14 | 100% | 100% | Mod to extend PP per Govt cause of delay | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1514 | 5046 | N/A | Repl Lighting Sys. HAS Ph-3 | HAS | HAS | 135.4401 | 53753485 | 54300000 | 53753485 | 396880.1337 | 1540800 | 11376.2468 | 2.87% | 2003-09-30 | 2003-09-30 | 2003-10-06 | 2004-03-15 | 2004-09-28 | See Mod01 | See Mod01 | Completed | b3h | 0 | Expired |  | DX50002165 | 2004-11-01 | 2004-10-04 | 2005-04-02 |  | GFP
|  | 3 | B | 03-1514 | 5046 | 1 | Repl Lighting Sys. HAS Ph-3 | HAS | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-02-26 | N/A | 2004-12-08 | 2004-09-28 | 100% | 100% | Mod to extend PP per Govt cause of delay | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | B | 03-1515 | 5047 | N/A | Repl Lighting Sys. HAS Ph-4 | HAS | HAS | 135.4401 | 41861753 | 42100000 | 41861753 | 309079.4602 | 963000 | 7110.1542 | 2.3% | 2003-09-30 | 2003-09-30 | 2003-10-06 | 2004-03-15 | 2004-09-28 | See Mod01 | See Mod01 | Completed | b3h | 0 | Expired |  | DX50002166 | 2004-11-01 | 2004-10-04 | 2005-04-02 |  | GFP
|  | 3 | B | 03-1515 | 5047 | 1 | Repl Lighting Sys. HAS Ph-4 | HAS | HAS | 135.4401 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-02-26 | N/A | 2004-12-08 | 2004-09-28 | 100% | 100% | Mod to extend PP per Govt cause of delay | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 3 | C | 87-5679 | CANX | N/A | Const Wall, Hateras Drive | Housing | Main Base | 135.4401 |  | 36379080 |  | 0 |  | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FY03 MOA not awarded (Cancelled) |  |  | Valid
|  | 3 | C | 03-1510 | CANX | N/A | Rpr Perimeter Fence, Base Beach | Beach | Main Base | 135.4401 |  | 59020000 |  | 0 |  | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FY03 MOA not awarded (Cancelled) |  |  | Valid
|  | 3 | C | 99-1019 | CANX | N/A | Rpr Walkway Lights, Dorms | Dorms | Main Base | 135.4401 |  | 54050000 |  | 0 |  | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FY03 MOA not awarded (Cancelled) |  |  | Valid
|  | 3 | C | 00-1020 | CANX | N/A | Rpr Doors/Walls, HASs | HAS | HAS | 135.4401 |  | 18362485 |  | 0 |  | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FY03 MOA not awarded (Cancelled) |  |  | Valid
|  | 3 | C | 68-4643 | CANX | N/A | Inst Keyless Entry System, Dorm | 673 | Main Base | 135.4401 |  | 27500000 |  | 0 |  | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FY03 MOA not awarded (Cancelled) |  |  | Valid
|  | 3 | C | 03-1136 | CANX | N/A | Cnst Dorm Storage | Dorms | Main Base | 135.4401 |  | 4600000 |  | 0 |  | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FY03 MOA not awarded (Cancelled) |  |  | Valid
|  | 3 | C | 02-1034 | CANX | N/A | Cnst Storage Shed | 3264 | HAS | 135.4401 |  | 3250000 |  | 0 |  | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FY03 MOA not awarded (Cancelled) |  |  | Valid
|  | 4 | 1 | 04-1064 | 5048 | N/A | Inst Male & Female Latrine | 645 | Main Base | 125.49 | 6200002 | 6200000 | 5989457 | 47728.56 | 0 | 0 | 0% | 2003-12-16 | 2004-03-19 | 2004-04-16 | 2004-07-14 | 2004-07-08 | 100% | 100% | Completed | b3h | 94 | Expired |  | DW40017957 | 2004-08-13 | 2004-07-20 | 2005-01-16 | Done
|  | 4 | 1 | 04-1067 | 5049 | N/A | Renovate Office & Bathroom | 651 | Main Base | 125.49 | 15212198 | 14100000 | 15137171 | 120624.5199 | 2408 | 19.1888 | 0.02% | 2003-12-16 | 2004-03-31 | 2004-04-02 | 2004-07-12 | 2004-07-12 | 100% | 100% | Completed | b3h | 106 | Expired |  | DW40018620 | 2004-08-27 | 2004-07-21 | 2005-01-17 | Done
|  | 4 | 1 | 03-1199 | 5050 | N/A | Rnv Magnums Restaurant | 486 | Main Base | 125.49 | 7529400 | 11000000 | 10584162 | 84342.6727 | 84049 | 669.7665 | 0.79% | 2004-01-06 | 2004-03-18 | 2004-03-19 | 2004-06-01 | 2004-05-11 | 100% | 100% | Completed | v2u | 72 | Expired |  | DW40014536 | 2004-06-28 | 2004-06-02 | 2004-11-29 | Done
|  | 4 | 1 | 04-1081 | 5051 | N/A | Upgrade Mechanical Rooms | 1500 | Sec Hill | 111.99 | 8511240 | 8700000 | 8497802 | 75880.0071 | 26750 | 238.8606 | 0.31% | 2004-02-06 | 2004-03-29 | 2004-04-02 | 2004-06-30 | 2004-06-30 | 100% | 100% | Completed | v2u | 52 | Expired |  | DW40018189 | 2004-08-19 | 2004-07-22 | 2005-01-18 | Done | MIPR AIA
|  | 4 | 1 | 04-1194 | 5053 | N/A | Improve Military Working Dog Kennel | 1003 | Main Base | 125.49 | 37647000 | 25500000 | 23831061 | 189904.0641 | 1792742 | 14285.9351 | 7.52% | 2004-02-24 | 2004-04-30 | 2004-05-10 | 2004-10-06 | 2004-10-06 | 100% | 100% | Completed | v2u | 66 | Expired | 2005-05-16 | DX50003844 | 2004-11-29 | 2004-11-03 | 2005-05-02
|  | 4 | 1 | 04-1192 | 5052 | N/A | Renovate 14 FS Vault | 3120 | HAS | 125.49 | 6274500 | 2600000 | 2662373 | 21215.818 | 0 | 0 | 0% | 2004-03-05 | 2004-04-26 | 2004-05-24 | 2004-07-21 | 2004-06-23 | 100% | 100% | Completed | v2u | 52 | Expired |  | DW40017221 | 2004-08-02 | 2004-07-09 | 2005-01-05 | Done
|  | 4 | 1 | 04-1527 | 5054 | N/A | Inst Lighting, LOX Cart Storage | A-14 | HAS | 125.49 | 2509800 | 2070000 | 2069643 | 16492.4934 | 0 | 0 | 0% | 2004-05-26 | 2004-06-07 | 2004-06-09 | 2004-08-09 | 2004-07-23 | 100% | 100% | Completed | v2u | 12 | Expired |  | DW40018246 | 2004-08-20 | 2004-07-26 | 2005-01-22 | Done
|  | 4 | 1 | 89-1541A | 5055 | N/A | Upgrade SATCOM Earth Terminal | 1500 | Sec Hill | 111.99 | 15433230 | 6750000 | 7023508 | 62715.4925 | 0 | 0 | 0% | 2004-05-27 | 2004-07-26 | 2004-07-27 | 2004-11-08 | 2004-10-27 | 100% | 100% | Completed | b3h | 60 | Expired |  | DX50005316 | 2004-12-10 | 2004-11-23 | 2005-05-22 |  | MIPR Hanscom AFB
|  | 4 | 1 | 05-4025 | 5056 | N/A | Rpr Sewer Line, Yosemite Dr. | Housing | Main Base | 125.49 | 25098000 | 35600000 | 36301976 | 289281.8233 | 355240 | 2830.8232 | 0.98% | 2004-08-03 | 2004-08-17 | 2004-08-17 | 2005-05-15 | 2005-05-12 | 100% | 100% | Waiting for invoice / Blue Book | v2u | 14 | Expired
|  | 4 | 1 | 05-4025 | 5056 | 1 | Rpr Sewer Line, Yosemite Dr. | Housing | Main Base | 125.49 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-10-04 | N/A | 2005-06-14 | 2005-05-12 | 100% | 100% | Mod to correct DSC and extend PP | v2u |  | Expired
|  | 4 | 1 | 05-4025 | 5056 | 2 | Rpr Sewer Line, Yosemite Dr. | Housing | Main Base | 125.49 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-10-04 | N/A | 2005-05-12 | 2005-05-12 | 100% | 100% | Mod to change Exclusion Period | v2u |  | Expired
|  | 4 | 1 | 04-7888 | 5057 | N/A | Upgrade Water Wells, Main Base | Misc. | Main Base | 125.49 | 7529400 | 5863000 | 6252200 | 49822.2966 | 91753 | 731.1579 | 1.47% | 2004-07-16 | 2004-09-14 | 2004-10-12 | 2005-02-08 | 2005-03-09 | N/A | N/A | Waiting for Paid Voucher | v2u | 60 | Expired |  | DX50013353 | 2005-04-07 | 2005-03-15 | 2005-09-11
|  | 4 | 1 | 04-7888 | 5057 | 1 | Upgrade Water Wells, Main Base | Misc. | Main Base | 125.49 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2004-11-17 | N/A | 2005-03-10 | 2005-03-09 | 100% | 100% | Mod to extend PP per Govt convenience | v2u |  | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 4 | 1 | 04-1197 | 5058 | N/A | Renovate Electrical System | 1742 | Main Base | 125.49 | 17816188 | 16300000 | 17816188 | 141972.97 | 0 | 0 | 0% | 2004-07-28 | 2004-09-08 | 2004-09-08 | 2004-11-08 | 2004-10-22 | See Mod01 | See Mod01 | Completed | b3h | 42 | Expired |  | DX50003845 | 2004-11-29 | 2004-11-02 | 2005-05-01
|  | 4 | 1 | 04-1197 | 5058 | 1 | Renovate Electrical System | 1742 | Main Base | 125.49 | 0 | -4329863 | -4357509 | -34723.9541 | 0 | 0 | -0% | N/A | 2004-09-16 | N/A | 2004-11-08 | 2004-10-22 | 100% | 100% | Completed | b3h |  | Expired |  | See DO | See DO | See DO | See DO | See DO
1 | 5059 | 4 | 1 | 04-1196 | 5059 | N/A | Const Cable Trough, MCOC Radome | 1522 | Sec Hill | 111.99 | 15230640 | 14900000 | 14244331 | 127192.8833 | 268570 | 2398.1606 | 1.89% | 2004-08-04 | 2004-09-17 | 2004-10-18 | 2005-07-18 |  | 50% | 90% | Performance in progress | v2u | 44 | [7 empty] | MIPR NSA
|  | 4 | 1 | 04-1196 | 5059 | 1 | Const Cable Trough, MCOC Radome | 1522 | Sec Hill | 111.99 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2005-06-02 | N/A | 2005-07-18 |  | 50% | 90% | Mod to change work condition - No cost | v2u | [8 empty] | MIPR NSA
2 | 5060 | 4 | 1 | 00-8003 | 5060 | N/A | Const Walkway Canopy, Sollars | 98 | Main Base | 125.49 | 18321540 | 17450000 | 17653536 | 140676.8348 | 338976 | 2701.2192 | 1.92% | 2004-08-04 | 2004-09-28 | 2004-10-28 | 2005-09-06 |  | 6% | 6% | Performance in progress | b3h | 55 | [7 empty] | MIPR DoDDS
|  | 4 | 1 | 04-1601 | 5061 | N/A | Repair Water Damage | 923 | Main Base | 125.49 | 5647050 | 5000000 | 4770806 | 38017.4197 | 12198 | 97.203 | 0.26% | 2004-08-12 | 2004-09-28 | 2004-09-28 | 2005-01-19 | 2004-12-15 | 100% | 100% | Completed | v2u | 47 | Expired |  | DX50009293 | 2005-02-10 | 2005-01-10 | 2005-07-09
|  | 4 | 1 | 04-1601 | 5061 | 1 | Repair Water Damage | 923 | Main Base | 125.49 | 627450 | 345000 | 313034 | 2494.4936 | 16050 | 127.8986 | 5.13% | 2004-11-02 | 2004-11-16 | N/A | N/A | 2004-12-15 | N/A | N/A | Mod for Addm No.1, Roof repair work | v2u | 14 | Expired |  | See DO | See DO | See DO | See DO | See DO
|  | 4 | 1 | 04-1601 | 5061 | 2 | Repair Water Damage | 923 | Main Base | 125.49 | 319000 | 265000 | 316218 | 2519.8661 | 0 | 0 | 0% | 2004-11-23 | 2004-12-13 | N/A | N/A | 2004-12-15 | N/A | N/A | Mod for Addm No.2,paint work | v2u | 20 | Expired |  | See DO | See DO | See DO | See DO | See DO
3 | 5064 | 4 | 1 | 04-1512 | 5064 | N/A | Renovate CONS Facility | 1006 | Main Base | 125.49 | 41526210 | 39912380 | 41526210 | 330912.503 | 60990 | 486.0148 | 0.15% | 2004-09-28 | 2004-09-28 | 2004-10-12 | 2005-06-27 |  | 99% | 99% | Final Insp scheduled on 12Jul05 | v2u | 0
|  | 4 | 1 | 04-1512 | 5064 | 1 | Renovate CONS Facility | 1006 | Main Base | 125.49 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2005-05-02 | N/A | 2005-07-29 |  | 99% | 99% | Mod to extend PP per Govt convenience | v2u
|  | 4 | 1 | 04-1513 | 5063 | N/A | Renovate TMF Facility | 653/656 | Main Base | 125.49 | 31840935 | 30150000 | 31840935 | 253732.8472 | 46545 | 370.906 | 0.15% | 2004-09-28 | 2004-09-28 | 2004-10-12 | 2005-04-29 | 2005-04-27 | 100% | 100% | Invoice submitted to DFAS | v2u | 0 | Expired |  | DX50014123 | 2005-04-21 | 2005-03-28 | 2005-09-24
|  | 4 | 1 | 04-1514 | 5062 | N/A | Renovate DAPS Facility | 1078 | Main Base | 125.49 | 15257401 | 15000000 | 15257401 | 121582.6042 | 168525 | 1342.9357 | 1.1% | 2004-09-28 | 2004-09-28 | 2004-10-12 | 2005-01-19 | 2005-03-15 | N/A | N/A | Waiting for invoice / Blue Book | v2u | 0 | Expired |  | See DO | See DO | See DO | See DO
|  | 4 | 1 | 04-1514 | 5062 | 1 | Renovate DAPS Facility | 1078 | Main Base | 125.49 | 2007840 | 1700000 | 1959369 | 15613.7461 | 0 | 0 | 0% | 2005-01-07 | 2005-01-18 | N/A | 2005-03-21 | 2005-03-15 | 100% | 100% | Waiting for invoice / Blue Book | v2u | 11 | Expired |  | See DO | See DO | See DO | See DO
4 | 5065 | 5 | 1 | 04-1196P2 | 5065 | N/A | Const Cable Trough, MCOC Radome P2 | 1500 | Sec Hill | 111.15 | 14570669 | 14600000 | 14570098 | 131085.0022 | 193670 | 1742.4202 | 1.33% | 2004-12-13 | 2004-12-22 | 2005-01-05 | 2005-08-02 |  | 90% | 90% | Performance in progress | v2u | 9 | [7 empty] | MIPR NSA
|  | 5 | 1 | 04-1196P2 | 5065 | 1 | Const Cable Trough, MCOC Radome P2 | 1500 | Sec Hill | 111.15 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | 2005-06-02 | N/A | 2005-08-02 |  | 90% | 90% | Mod to change work condition - No cost | v2u | [8 empty] | MIPR NSA
|  | 5 | 1 | 05-1088 | 5066 | N/A | Rpr Floor Tile | 600/622 | Main Base | 125.49 | 1631370 | 1280000 | 1617123 | 12886.469 | 42800 | 341.063 | 2.65% | 2005-01-28 | 2005-02-08 | 2005-02-09 | 2005-03-25 | 2005-03-16 | 100% | 100% | Under Warranty | v2u | 11 | Expired |  | DX50013857 | 2005-04-15 | 2005-03-18 | 2005-09-14
|  | 5 | 1 | 05-1082 | 5067 | N/A | Repair Electrical System | 650 | Main Base | 125.49 | 1500000 | 1203000 | 1242709 | 9902.8528 | 0 | 0 | 0% | 2005-01-26 | 2005-02-09 | 2005-02-10 | 2005-03-28 | 2005-03-07 | 100% | 100% | Waiting for Paid Voucher | v2u | 14 | Expired |  | DX50013090 | 2005-04-04 | 2005-03-10 | 2005-09-06
|  | 5 | 2 | 03-1123AF | 5068 | N/A | Repaint Exterior, Selected Bldgs | Misc. | Ripsaw | 125.49 | 14240000 | 11100000 | 10143409 | 80830.4168 | 199876 | 1592.7644 | 1.97% | 2005-01-26 | 2005-03-18 | 2005-04-01 | 2005-06-29 | 2005-06-28 | 100% | 100% | Waiting for invoice | v2u | 51 | Expired
5 | 5069 | 5 | 2 | 05-4054 | 5069 | N/A | Rpr Fire Damage, MFH | Q 114D | Main Base | 125.49 | 10666650 | 9640000 | 10562038 | 84166.3718 | 305967 | 2438.1783 | 2.9% | 2005-05-12 | 2005-07-06 | 2005-07-07 | 2005-11-14 |  | 0% | 0% | NTP on 7Jul | v2b | 55
6 | 5070 | 5 | 2 | 05-1725 | 5070 | N/A | Inst Heat/Roll-up Door | 948 | Main Base | 125.49 | 12172530 | 12000000 | 11956923 | 95281.879 | 252520 | 2012.2719 | 2.11% | 2005-05-11 | 2005-07-06 | 2005-07-07 | 2005-10-14 |  | 0% | 0% | NTP on 7Jul | v2b | 56
Formulas:
COMPLETIONDATE = [NTPDATE]+119
COMPLETIONDATE = IF([NTPDATE]="","",[NTPDATE]+149)
CALT = IF(ISERROR(TODAY()-[PR Date]),"",IF([PR Date]="","",IF([Awd Date]="",TODAY()-[PR Date],[Awd Date]-[PR Date])))
CALT = IF(ISERROR(IF([PR Date]="","",IF([Awd Date]="",TODAY()-[PR Date],[Awd Date]-[PR Date]))),"",IF([PR Date]="","",IF([Awd Date]="",TODAY()-[PR Date],[Awd Date]-[PR Date])))
Warranty = IF([ACCEPTANCE]>TODAY()-365,"Valid",IF([ACCEPTANCE]="","",IF([ACCEPTANCE]<TODAY()-365,"Expired","Valid")))
Close-Out = IF(ISERROR([Final Accept]/1),[Final Accept],IF([Final Accept]="","",[Final Accept]+180))
ACCEPTANCE = [ACCEPTANCE, row above]
ACCEPTANCE = [ACCEPTANCE, row below]
Note on D14: B: Base Year, 1: Option Year 1, 2: Option Year 2, 3: Option Year 3 and M: MOA, C: Cancelled
Note on F14: Black Bold: DO#, intial award. Black Normal: DO# accompanying Mod. Red Bold: DO# researved due to RTA CANX = Project cancelled
Note on G14: Mod #. N/A = initial award
Note on V14: Date in light gray indicates original or previous completion date changed by Mod.
Note on X5: Upon award, insert 0% in the Schedule and the Actual.
Note on AD14: Enter the date of warranty repair if ocurred. If no, leave blank.
Note on AG14: Insert the date of final acceptance notice. Final invoice, release of claim, and as-built must be obtained prior to the notice.
Note on AH14: Close out within 180 days after the date of final acceptance notice.
Warranty Period Expired
DO Closed Out
Final Inspection Completed
Check! Progress
Check! Bond

## PB Tracker
| Performance Bond Tracker (SABER, F62509-03-D-0002) | [11 empty] | Performance Bond Tracker
| Current Coverage: |  |  |  | 300000000 |  |  | as of
| Active DOs: |  |  |  | 110513136 |  |  | 2026-07-30 |  | Legend
| Extra Bonding: |  |  |  | 189486864
| Add'l Required: |  |  |  | 0
PB Log
| Enter Date |  |  | PB Balance |  |  | Enter Bond Inc/Dec |  | Remarks
| 2003-01-14 |  |  | 53360000 |  |  |  |  | Basic PB for minimum guaranteed amount.
| 2003-04-17 |  |  | 253360000 |  |  | 200000000 |  | Additional bonding obtained.
| 2003-07-01 |  |  | 403360000 |  |  | 150000000 |  | Additional bonding obtained.
| 2003-08-26 |  |  | 763360000 |  |  | 360000000 |  | Additional bonding obtained.
| 2003-10-06 |  |  | 874360000 |  |  | 111000000 |  | Additional bonding obtained.
| 2004-01-09 |  |  | 763360000 |  |  | -111000000 |  | Excess bonding deducted.
| 2004-08-03 |  |  | 403360000 |  |  | -360000000 |  | Excess bonding deducted.
| 2005-02-24 |  |  | 300000000 |  |  | -103360000 |  | Excess bonding deducted.
| Automated PB Tracker (DO "Sort" data by Awd Date) | [7 empty] | Criteria
# | FY | YR | QKKA | DO# | Mod | Award (¥) | Awd Date | Final Date | Final Date | Cum. Awd Amt | Cum. Complete Amt | Active DO Amount | (Init'l PB) minus (Active DOs) | Bond Inc / Dec | Bond Secured | Criteria Awd YYYYM | Criteria Completed YYYYM | Ser
2 | 3 | B | 03-1060 | 5001 | N/A | 6754687 | 2003-03-27 | 2003-05-13 | <=37707 | 6754687 | 0 | 6754687 | 46605313 |  | 53360000 | 200303 | 200305 | 2
5 | 3 | B | 02-1067 | 5003 | N/A | 6601584 | 2003-03-27 | 2003-05-30 | <=37707 | 13356271 | 0 | 13356271 | 40003729 |  | 53360000 | 200303 | 200305 | 5
3 | 3 | B | 03-1184 | 5002 | N/A | 3188160 | 2003-03-28 | 2003-04-23 | <=37708 | 16544431 | 0 | 16544431 | 36815569 |  | 53360000 | 200303 | 200304 | 3
6 | 3 | B | 03-5007 | 5004 | N/A | 14337206 | 2003-04-01 | 2003-05-09 | <=37712 | 30881637 | 0 | 30881637 | 22478363 |  | 53360000 | 200304 | 200305 | 6
1 | 3 | B | 03-1040 | 5000 | N/A | 8221240 | 2003-04-03 | 2003-07-11 | <=37714 | 39102877 | 0 | 39102877 | 14257123 |  | 53360000 | 200304 | 200307 | 1
8 | 3 | B | 03-1183 | 5005 | N/A | 1886889 | 2003-04-03 | 2003-05-21 | <=37714 | 40989766 | 0 | 40989766 | 12370234 |  | 53360000 | 200304 | 200305 | 8
9 | 3 | B | 03-1068 | 5006 | N/A | 998500 | 2003-04-03 | 2003-05-01 | <=37714 | 41988266 | 0 | 41988266 | 11371734 |  | 53360000 | 200304 | 200305 | 9
4 | 3 | B | 03-1184 | 5002 | 1 | 0 | 2003-04-07 | 2003-04-23 | <=37718 | 41988266 | 0 | 41988266 | 11371734 |  | 53360000 | 200304 | 200304 | 4
7 | 3 | B | 03-5007 | 5004 | 1 | -1281 | 2003-04-09 | 2003-05-09 | <=37720 | 41986985 | 0 | 41986985 | 11373015 | 200000000 | 253360000 | 200304 | 200305 | 7
10 | 3 | B | 03-1039 | 5007 | N/A | 20821107 | 2003-04-18 | 2003-09-04 | <=37729 | 62808092 | 0 | 62808092 | -9448092 |  | 253360000 | 200304 | 200309 | 10
12 | 3 | B | 03-1039 | 5007 | 1 | -317561 | 2003-04-23 | 2003-09-04 | <=37734 | 62490531 | 3188160 | 59302371 | -5942371 |  | 253360000 | 200304 | 200309 | 12
13 | 3 | B | 03-1169 | 5008 | N/A | 3783610 | 2003-05-02 | 2003-08-07 | <=37743 | 66274141 | 4186660 | 62087481 | -8727481 |  | 253360000 | 200305 | 200308 | 13
14 | 3 | B | 02-1030 | 5009 | N/A | 48792291 | 2003-05-02 | 2003-11-12 | <=37743 | 115066432 | 4186660 | 110879772 | -57519772 |  | 253360000 | 200305 | 200311 | 14
16 | 3 | B | 03-1065 | 5010 | N/A | 5551713 | 2003-05-28 | 2003-07-24 | <=37769 | 120618145 | 27164161 | 93453984 | -40093984 |  | 253360000 | 200305 | 200307 | 16
18 | 3 | B | 44-4867 | 5011 | N/A | 30106297 | 2003-06-04 | 2003-09-22 | <=37776 | 150724442 | 33765745 | 116958697 | -63598697 |  | 253360000 | 200306 | 200309 | 18
19 | 3 | B | 03-1052B | 5012 | N/A | 5755580 | 2003-06-04 | 2003-09-10 | <=37776 | 156480022 | 33765745 | 122714277 | -69354277 |  | 253360000 | 200306 | 200309 | 19
21 | 3 | B | 03-1044 | 5013 | N/A | 21736968 | 2003-06-06 | 2003-10-17 | <=37778 | 178216990 | 33765745 | 144451245 | -91091245 |  | 253360000 | 200306 | 200310 | 21
23 | 3 | B | 13-5857 | 5015 | N/A | 4828528 | 2003-06-12 | 2003-09-04 | <=37784 | 183045518 | 33765745 | 149279773 | -95919773 |  | 253360000 | 200306 | 200309 | 23
17 | 3 | B | 03-1065 | 5010 | 1 | 0 | 2003-06-16 | 2003-07-24 | <=37788 | 183045518 | 33765745 | 149279773 | -95919773 |  | 253360000 | 200306 | 200307 | 17
26 | 3 | B | 03-5007A | 5016 | N/A | 59572139 | 2003-06-16 | 2003-12-12 | <=37788 | 242617657 | 33765745 | 208851912 | -155491912 |  | 253360000 | 200306 | 200312 | 26
22 | 3 | B | 03-1069 | 5014 | N/A | 6303874 | 2003-06-17 | 2003-07-25 | <=37789 | 248921531 | 33765745 | 215155786 | -161795786 |  | 253360000 | 200306 | 200307 | 22
28 | 3 | B | 03-1192B | 5017 | N/A | 16684948 | 2003-06-20 | 2003-12-02 | <=37792 | 265606479 | 33765745 | 231840734 | -178480734 |  | 253360000 | 200306 | 200312 | 28
30 | 3 | B | 97-1048 | 5018 | N/A | 31976784 | 2003-06-20 | 2003-10-30 | <=37792 | 297583263 | 33765745 | 263817518 | -210457518 |  | 253360000 | 200306 | 200310 | 30
31 | 3 | B | 01-0007 | 5019 | N/A | 22955537 | 2003-06-20 | 2003-10-30 | <=37792 | 320538800 | 33765745 | 286773055 | -233413055 |  | 253360000 | 200306 | 200310 | 31
32 | 3 | B | 01-0007 | 5019 | 1 | 0 | 2003-06-20 | 2003-10-30 | <=37792 | 320538800 | 33765745 | 286773055 | -233413055 |  | 253360000 | 200306 | 200310 | 32
33 | 3 | B | 03-1041 | 5020 | N/A | 10687433 | 2003-06-23 | 2003-11-21 | <=37795 | 331226233 | 33765745 | 297460488 | -244100488 |  | 253360000 | 200306 | 200311 | 33
35 | 3 | B | 13-5857B | 5021 | N/A | 10047296 | 2003-06-30 | 2003-11-06 | <=37802 | 341273529 | 33765745 | 307507784 | -254147784 | 150000000 | 403360000 | 200306 | 200311 | 35
38 | 3 | B | 03-1192A | 5022 | N/A | 35063415 | 2003-07-03 | 2004-03-30 | <=37805 | 376336944 | 33765745 | 342571199 | -289211199 |  | 403360000 | 200307 | 200403 | 38
25 | 3 | B | 13-5857 | 5015 | 1 | 0 | 2003-07-18 | 2003-09-04 | <=37820 | 376336944 | 41986985 | 334349959 | -280989959 |  | 403360000 | 200307 | 200309 | 25
41 | 3 | B | 83-5850B | 5023 | N/A | 28415428 | 2003-07-25 | 2003-11-12 | <=37827 | 404752372 | 53842572 | 350909800 | -297549800 |  | 403360000 | 200307 | 200311 | 41
44 | 3 | B | 03-1140 | 5024 | N/A | 90906615 | 2003-07-25 | 2004-06-30 | <=37827 | 495658987 | 53842572 | 441816415 | -388456415 |  | 403360000 | 200307 | 200406 | 44
47 | 3 | B | 03-1140B | 5025 | N/A | 86892325 | 2003-07-25 | 2004-02-17 | <=37827 | 582551312 | 53842572 | 528708740 | -475348740 |  | 403360000 | 200307 | 200402 | 47
50 | 3 | B | 03-1140C | 5026 | N/A | 76634236 | 2003-07-25 | 2004-05-13 | <=37827 | 659185548 | 53842572 | 605342976 | -551982976 |  | 403360000 | 200307 | 200405 | 50
53 | 3 | B | 03-1511 | 5027 | N/A | 37365622 | 2003-07-25 | 2004-03-08 | <=37827 | 696551170 | 53842572 | 642708598 | -589348598 |  | 403360000 | 200307 | 200403 | 53
55 | 3 | B | 03-1512 | 5028 | N/A | 35228647 | 2003-07-25 | 2004-08-12 | <=37827 | 731779817 | 53842572 | 677937245 | -624577245 |  | 403360000 | 200307 | 200408 | 55
58 | 3 | B | 03-1196 | 5029 | N/A | 26771061 | 2003-08-08 | 2003-12-24 | <=37841 | 758550878 | 57626182 | 700924696 | -647564696 |  | 403360000 | 200308 | 200312 | 58
39 | 3 | B | 03-1192A | 5022 | 1 | 270009 | 2003-08-26 | 2004-03-30 | <=37859 | 758820887 | 57626182 | 701194705 | -647834705 | 360000000 | 763360000 | 200308 | 200403 | 39
20 | 3 | B | 03-1052B | 5012 | 1 | 1247205 | 2003-08-28 | 2003-09-10 | <=37861 | 760068092 | 57626182 | 702441910 | -649081910 |  | 763360000 | 200308 | 200309 | 20
11 | 3 | B | 03-1039 | 5007 | 2 | 2886508 | 2003-08-29 | 2003-09-04 | <=37862 | 762954600 | 57626182 | 705328418 | -651968418 |  | 763360000 | 200308 | 200309 | 11
37 | 3 | B | 13-5857B | 5021 | 1 | 0 | 2003-09-03 | 2003-11-06 | <=37867 | 762954600 | 57626182 | 705328418 | -651968418 |  | 763360000 | 200309 | 200311 | 37
63 | 3 | B | 31-6456 | 5031 | N/A | 3419826 | 2003-09-08 | 2004-03-30 | <=37872 | 766374426 | 85844764 | 680529662 | -627169662 |  | 763360000 | 200309 | 200403 | 63
24 | 3 | B | 13-5857 | 5015 | 2 | 0 | 2003-09-11 | 2003-09-04 | <=37875 | 766374426 | 92847549 | 673526877 | -620166877 |  | 763360000 | 200309 | 200309 | 24
36 | 3 | B | 13-5857B | 5021 | 2 | 0 | 2003-09-11 | 2003-11-06 | <=37875 | 766374426 | 92847549 | 673526877 | -620166877 |  | 763360000 | 200309 | 200311 | 36
45 | 3 | B | 03-1140 | 5024 | 1 | 0 | 2003-09-11 | 2004-06-30 | <=37875 | 766374426 | 92847549 | 673526877 | -620166877 |  | 763360000 | 200309 | 200406 | 45
48 | 3 | B | 03-1140B | 5025 | 1 | 0 | 2003-09-11 | 2004-02-17 | <=37875 | 766374426 | 92847549 | 673526877 | -620166877 |  | 763360000 | 200309 | 200402 | 48
51 | 3 | B | 03-1140C | 5026 | 1 | 0 | 2003-09-11 | 2004-04-16 | <=37875 | 766374426 | 92847549 | 673526877 | -620166877 |  | 763360000 | 200309 | 200404 | 51
60 | 3 | B | 03-8007 | 5030 | N/A | 8761002 | 2003-09-15 | 2004-07-20 | <=37879 | 775135428 | 92847549 | 682287879 | -628927879 |  | 763360000 | 200309 | 200407 | 60
42 | 3 | B | 83-5850B | 5023 | 1 | -13215584 | 2003-09-16 | 2003-11-12 | <=37880 | 761919844 | 92847549 | 669072295 | -615712295 |  | 763360000 | 200309 | 200311 | 42
61 | 3 | B | 03-8007 | 5030 | 1 | 0 | 2003-09-17 | 2004-07-20 | <=37881 | 761919844 | 92847549 | 669072295 | -615712295 |  | 763360000 | 200309 | 200407 | 61
66 | 3 | B | 03-1191 | 5032 | N/A | 2790425 | 2003-09-18 | 2003-11-21 | <=37882 | 764710269 | 92847549 | 671862720 | -618502720 |  | 763360000 | 200309 | 200311 | 66
68 | 3 | B | 03-1189 | 5033 | N/A | 1219478 | 2003-09-18 | 2003-10-08 | <=37882 | 765929747 | 92847549 | 673082198 | -619722198 |  | 763360000 | 200309 | 200310 | 68
69 | 3 | B | 03-1190 | 5034 | N/A | 554631 | 2003-09-18 | 2003-10-30 | <=37882 | 766484378 | 92847549 | 673636829 | -620276829 |  | 763360000 | 200309 | 200310 | 69
64 | 3 | B | 31-6456 | 5031 | 1 | 156386 | 2003-09-19 | 2004-03-30 | <=37883 | 766640764 | 92847549 | 673793215 | -620433215 |  | 763360000 | 200309 | 200403 | 64
71 | 3 | B | 03-1193 | 5035 | N/A | 23047922 | 2003-09-19 | 2004-07-20 | <=37883 | 789688686 | 92847549 | 696841137 | -643481137 |  | 763360000 | 200309 | 200407 | 71
72 | 3 | B | 03-8015 | 5036 | N/A | 1530717 | 2003-09-19 | 2003-12-24 | <=37883 | 791219403 | 92847549 | 698371854 | -645011854 |  | 763360000 | 200309 | 200312 | 72
73 | 3 | B | 02-4002 | 5037 | N/A | 5444629 | 2003-09-19 | 2004-07-13 | <=37883 | 796664032 | 92847549 | 703816483 | -650456483 |  | 763360000 | 200309 | 200407 | 73
75 | 3 | B | 04-1035 | 5038 | N/A | 69446362 | 2003-09-20 | 2004-07-29 | <=37884 | 866110394 | 92847549 | 773262845 | -719902845 |  | 763360000 | 200309 | 200407 | 75
29 | 3 | B | 03-1192B | 5017 | 1 | 2860828 | 2003-09-24 | 2003-12-02 | <=37888 | 868971222 | 122953846 | 746017376 | -692657376 |  | 763360000 | 200309 | 200312 | 29
76 | 3 | B | 04-1035 | 5038 | 1 | 3010494 | 2003-09-24 | 2004-07-29 | <=37888 | 871981716 | 122953846 | 749027870 | -695667870 |  | 763360000 | 200309 | 200407 | 76
15 | 3 | B | 02-1030 | 5009 | 1 | -120840 | 2003-09-25 | 2003-11-12 | <=37889 | 871860876 | 122953846 | 748907030 | -695547030 |  | 763360000 | 200309 | 200311 | 15
27 | 3 | B | 03-5007A | 5016 | 1 | 5324227 | 2003-09-25 | 2003-12-12 | <=37889 | 877185103 | 122953846 | 754231257 | -700871257 |  | 763360000 | 200309 | 200312 | 27
79 | 3 | B | 00-8017 | 5039 | N/A | 22042357 | 2003-09-25 | 2004-08-10 | <=37889 | 899227460 | 122953846 | 776273614 | -722913614 |  | 763360000 | 200309 | 200408 | 79
80 | 3 | B | 03-8012 | 5040 | N/A | 16179627 | 2003-09-25 | 2004-08-03 | <=37889 | 915407087 | 122953846 | 792453241 | -739093241 |  | 763360000 | 200309 | 200408 | 80
77 | 3 | B | 04-1035 | 5038 | 2 | 0 | 2003-09-27 | 2004-07-29 | <=37891 | 915407087 | 122953846 | 792453241 | -739093241 |  | 763360000 | 200309 | 200407 | 77
85 | 3 | B | 02-1133 | 5043 | N/A | 19146407 | 2003-09-27 | 2004-08-04 | <=37891 | 934553494 | 122953846 | 811599648 | -758239648 |  | 763360000 | 200309 | 200408 | 85
43 | 3 | B | 83-5850B | 5023 | 2 | 0 | 2003-09-29 | 2003-11-12 | <=37893 | 934553494 | 122953846 | 811599648 | -758239648 |  | 763360000 | 200309 | 200311 | 43
81 | 3 | B | 03-1517 | 5041 | N/A | 9430386 | 2003-09-29 | 2004-06-09 | <=37893 | 943983880 | 122953846 | 821030034 | -767670034 |  | 763360000 | 200309 | 200406 | 81
84 | 3 | B | 03-1518 | 5042 | N/A | 6636004 | 2003-09-29 | 2003-12-04 | <=37893 | 950619884 | 122953846 | 827666038 | -774306038 |  | 763360000 | 200309 | 200312 | 84
87 | 3 | B | 03-5009 | 5044 | N/A | 13378413 | 2003-09-29 | 2004-01-30 | <=37893 | 963998297 | 122953846 | 841044451 | -787684451 |  | 763360000 | 200309 | 200401 | 87
56 | 3 | B | 03-1512 | 5028 | 1 | 17533643 | 2003-09-30 | 2004-08-12 | <=37894 | 981531940 | 122953846 | 858578094 | -805218094 |  | 763360000 | 200309 | 200408 | 56
89 | 3 | B | 03-1513 | 5045 | N/A | 44151791 | 2003-09-30 | 2004-09-14 | <=37894 | 1025683731 | 122953846 | 902729885 | -849369885 |  | 763360000 | 200309 | 200409 | 89
91 | 3 | B | 03-1514 | 5046 | N/A | 53753485 | 2003-09-30 | 2004-09-28 | <=37894 | 1079437216 | 122953846 | 956483370 | -903123370 |  | 763360000 | 200309 | 200409 | 91
93 | 3 | B | 03-1515 | 5047 | N/A | 41861753 | 2003-09-30 | 2004-09-28 | <=37894 | 1121298969 | 122953846 | 998345123 | -944985123 | 111000000 | 874360000 | 200309 | 200409 | 93
70 | 3 | B | 03-1190 | 5034 | 1 | 0 | 2003-10-14 | 2003-10-30 | <=37908 | 1121298969 | 124173324 | 997125645 | -943765645 |  | 874360000 | 200310 | 200310 | 70
34 | 3 | B | 03-1041 | 5020 | 1 | 0 | 2003-10-21 | 2003-11-21 | <=37915 | 1121298969 | 145910292 | 975388677 | -922028677 |  | 874360000 | 200310 | 200311 | 34
67 | 3 | B | 03-1191 | 5032 | 1 | 0 | 2003-10-23 | 2003-11-21 | <=37917 | 1121298969 | 145910292 | 975388677 | -922028677 |  | 874360000 | 200310 | 200311 | 67
46 | 3 | B | 03-1140 | 5024 | 2 | 0 | 2003-11-14 | 2004-06-30 | <=37939 | 1121298969 | 275315835 | 845983134 | -792623134 |  | 874360000 | 200311 | 200406 | 46
49 | 3 | B | 03-1140B | 5025 | 2 | 0 | 2003-11-14 | 2004-02-17 | <=37939 | 1121298969 | 275315835 | 845983134 | -792623134 |  | 874360000 | 200311 | 200402 | 49
52 | 3 | B | 03-1140C | 5026 | 2 | 0 | 2003-11-14 | 2004-04-16 | <=37939 | 1121298969 | 275315835 | 845983134 | -792623134 |  | 874360000 | 200311 | 200404 | 52
54 | 3 | B | 03-1511 | 5027 | 1 | 0 | 2003-11-14 | 2004-03-08 | <=37939 | 1121298969 | 275315835 | 845983134 | -792623134 |  | 874360000 | 200311 | 200403 | 54
59 | 3 | B | 03-1196 | 5029 | 1 | 0 | 2003-12-02 | 2003-12-24 | <=37957 | 1121298969 | 308339469 | 812959500 | -759599500 |  | 874360000 | 200312 | 200312 | 59
82 | 3 | B | 03-1517 | 5041 | 1 | 0 | 2003-12-02 | 2004-06-09 | <=37957 | 1121298969 | 308339469 | 812959500 | -759599500 |  | 874360000 | 200312 | 200406 | 82
88 | 3 | B | 03-5009 | 5044 | 1 | 957487 | 2003-12-18 | 2004-01-30 | <=37973 | 1122256456 | 379871839 | 742384617 | -689024617 | -111000000 | 763360000 | 200312 | 200401 | 88
40 | 3 | B | 03-1192A | 5022 | 2 | -730876 | 2004-02-10 | 2004-03-30 | <=38027 | 1121525580 | 422509517 | 699016063 | -645656063 |  | 763360000 | 200402 | 200403 | 40
65 | 3 | B | 31-6456 | 5031 | 2 | 156386 | 2004-02-10 | 2004-03-30 | <=38027 | 1121681966 | 422509517 | 699172449 | -645812449 |  | 763360000 | 200402 | 200403 | 65
57 | 3 | B | 03-1512 | 5028 | 3 | 0 | 2004-02-26 | 2004-08-12 | <=38043 | 1121681966 | 509401842 | 612280124 | -558920124 |  | 763360000 | 200402 | 200408 | 57
90 | 3 | B | 03-1513 | 5045 | 1 | 0 | 2004-02-26 | 2004-09-14 | <=38043 | 1121681966 | 509401842 | 612280124 | -558920124 |  | 763360000 | 200402 | 200409 | 90
92 | 3 | B | 03-1514 | 5046 | 1 | 0 | 2004-02-26 | 2004-09-28 | <=38043 | 1121681966 | 509401842 | 612280124 | -558920124 |  | 763360000 | 200402 | 200409 | 92
94 | 3 | B | 03-1515 | 5047 | 1 | 0 | 2004-02-26 | 2004-09-28 | <=38043 | 1121681966 | 509401842 | 612280124 | -558920124 |  | 763360000 | 200402 | 200409 | 94
104 | 4 | 1 | 03-1199 | 5050 | N/A | 10584162 | 2004-03-18 | 2004-05-11 | <=38064 | 1132266128 | 546767464 | 585498664 | -532138664 |  | 763360000 | 200403 | 200405 | 104
102 | 4 | 1 | 04-1064 | 5048 | N/A | 5989457 | 2004-03-19 | 2004-07-08 | <=38065 | 1138255585 | 546767464 | 591488121 | -538128121 |  | 763360000 | 200403 | 200407 | 102
105 | 4 | 1 | 04-1081 | 5051 | N/A | 8497802 | 2004-03-29 | 2004-06-30 | <=38075 | 1146753387 | 546767464 | 599985923 | -546625923 |  | 763360000 | 200403 | 200406 | 105
103 | 4 | 1 | 04-1067 | 5049 | N/A | 15137171 | 2004-03-31 | 2004-07-12 | <=38077 | 1161890558 | 585102610 | 576787948 | -523427948 |  | 763360000 | 200403 | 200407 | 103
78 | 3 | B | 04-1035 | 5038 | 3 | 0 | 2004-04-19 | 2004-07-29 | <=38096 | 1161890558 | 585102610 | 576787948 | -523427948 |  | 763360000 | 200404 | 200407 | 78
107 | 4 | 1 | 04-1192 | 5052 | N/A | 2662373 | 2004-04-26 | 2004-06-23 | <=38103 | 1164552931 | 585102610 | 579450321 | -526090321 |  | 763360000 | 200404 | 200406 | 107
106 | 4 | 1 | 04-1194 | 5053 | N/A | 23831061 | 2004-04-30 | 2004-10-06 | <=38107 | 1188383992 | 585102610 | 603281382 | -549921382 |  | 763360000 | 200404 | 200410 | 106
74 | 3 | B | 02-4002 | 5037 | 1 | -4060 | 2004-05-07 | 2004-07-13 | <=38114 | 1188379932 | 585102610 | 603277322 | -549917322 |  | 763360000 | 200405 | 200407 | 74
108 | 4 | 1 | 04-1527 | 5054 | N/A | 2069643 | 2004-06-07 | 2004-07-23 | <=38145 | 1190449575 | 672321008 | 518128567 | -464768567 |  | 763360000 | 200406 | 200407 | 108
83 | 3 | B | 03-1517 | 5041 | 2 | -1108526 | 2004-06-09 | 2004-06-09 | <=38147 | 1189341049 | 680642868 | 508698181 | -455338181 |  | 763360000 | 200406 | 200406 | 83
86 | 3 | B | 02-1133 | 5043 | 1 | -96 | 2004-06-17 | 2004-08-04 | <=38155 | 1189340953 | 680642868 | 508698085 | -455338085 |  | 763360000 | 200406 | 200408 | 86
62 | 3 | B | 03-8007 | 5030 | 2 | 0 | 2004-07-12 | 2004-07-20 | <=38180 | 1189340953 | 803836286 | 385504667 | -332144667 |  | 763360000 | 200407 | 200407 | 62
109 | 4 | 1 | 89-1541A | 5055 | N/A | 7023508 | 2004-07-26 | 2004-10-27 | <=38194 | 1196364461 | 843155422 | 353209039 | -299849039 | -360000000 | 403360000 | 200407 | 200410 | 109
110 | 4 | 1 | 05-4025 | 5056 | N/A | 36301976 | 2004-08-17 | 2005-05-12 | <=38216 | 1232666437 | 1025742863 | 206923574 | -153563574 |  | 403360000 | 200408 | 200505 | 110
115 | 4 | 1 | 04-1197 | 5058 | N/A | 17816188 | 2004-09-08 | 2004-10-22 | <=38238 | 1250482625 | 1025742863 | 224739762 | -171379762 |  | 403360000 | 200409 | 200410 | 115
113 | 4 | 1 | 04-7888 | 5057 | N/A | 6252200 | 2004-09-14 | 2005-03-09 | <=38244 | 1256734825 | 1069894654 | 186840171 | -133480171 |  | 403360000 | 200409 | 200503 | 113
116 | 4 | 1 | 04-1197 | 5058 | 1 | -4357509 | 2004-09-16 | 2004-10-22 | <=38246 | 1252377316 | 1069894654 | 182482662 | -129122662 |  | 403360000 | 200409 | 200410 | 116
117 | 4 | 1 | 04-1196 | 5059 | N/A | 14244331 | 2004-09-17 |  | <=38247 | 1266621647 | 1069894654 | 196726993 | -143366993 |  | 403360000 | 200409 |  | 117
118 | 4 | 1 | 00-8003 | 5060 | N/A | 17653536 | 2004-09-28 |  | <=38258 | 1284275183 | 1165509892 | 118765291 | -65405291 |  | 403360000 | 200409 |  | 118
119 | 4 | 1 | 04-1601 | 5061 | N/A | 4770806 | 2004-09-28 | 2004-12-15 | <=38258 | 1289045989 | 1165509892 | 123536097 | -70176097 |  | 403360000 | 200409 | 200412 | 119
122 | 4 | 1 | 04-1512 | 5064 | N/A | 41526210 | 2004-09-28 |  | <=38258 | 1330572199 | 1165509892 | 165062307 | -111702307 |  | 403360000 | 200409 |  | 122
123 | 4 | 1 | 04-1513 | 5063 | N/A | 31840935 | 2004-09-28 | 2005-04-27 | <=38258 | 1362413134 | 1165509892 | 196903242 | -143543242 |  | 403360000 | 200409 | 200504 | 123
124 | 4 | 1 | 04-1514 | 5062 | N/A | 15257401 | 2004-09-28 | 2005-03-15 | <=38258 | 1377670535 | 1165509892 | 212160643 | -158800643 |  | 403360000 | 200409 | 200503 | 124
111 | 4 | 1 | 05-4025 | 5056 | 1 | 0 | 2004-10-04 | 2005-05-12 | <=38264 | 1377670535 | 1165509892 | 212160643 | -158800643 |  | 403360000 | 200410 | 200505 | 111
112 | 4 | 1 | 05-4025 | 5056 | 2 | 0 | 2004-10-04 | 2005-05-12 | <=38264 | 1377670535 | 1165509892 | 212160643 | -158800643 |  | 403360000 | 200410 | 200505 | 112
120 | 4 | 1 | 04-1601 | 5061 | 1 | 313034 | 2004-11-16 | 2004-12-15 | <=38307 | 1377983569 | 1209823140 | 168160429 | -114800429 |  | 403360000 | 200411 | 200412 | 120
114 | 4 | 1 | 04-7888 | 5057 | 1 | 0 | 2004-11-17 | 2005-03-09 | <=38308 | 1377983569 | 1209823140 | 168160429 | -114800429 |  | 403360000 | 200411 | 200503 | 114
121 | 4 | 1 | 04-1601 | 5061 | 2 | 316218 | 2004-12-13 | 2004-12-15 | <=38334 | 1378299787 | 1209823140 | 168476647 | -115116647 |  | 403360000 | 200412 | 200412 | 121
126 | 5 | 1 | 04-1196P2 | 5065 | N/A | 14570098 | 2004-12-22 |  | <=38343 | 1392869885 | 1215223198 | 177646687 | -124286687 |  | 403360000 | 200412 |  | 126
125 | 4 | 1 | 04-1514 | 5062 | 1 | 1959369 | 2005-01-18 | 2005-03-15 | <=38370 | 1394829254 | 1215223198 | 179606056 | -126246056 |  | 403360000 | 200501 | 200503 | 125
127 | 5 | 1 | 05-1088 | 5066 | N/A | 1617123 | 2005-02-08 | 2005-03-16 | <=38391 | 1396446377 | 1215223198 | 181223179 | -127863179 |  | 403360000 | 200502 | 200503 | 127
128 | 5 | 1 | 05-1082 | 5067 | N/A | 1242709 | 2005-02-09 | 2005-03-07 | <=38392 | 1397689086 | 1215223198 | 182465888 | -129105888 | -103360000 | 300000000 | 200502 | 200503 | 128
129 | 5 | 2 | 03-1123AF | 5068 | N/A | 10143409 | 2005-03-18 | 2005-06-28 | <=38429 | 1407832495 | 1241552000 | 166280495 | -112920495 |  | 300000000 | 200503 | 200506 | 129
130 | 5 | 2 | 05-4054 | 5069 | N/A | 10562038 | 2005-07-06 |  | <=38539 | 1418394533 | 1319838320 | 98556213 | -45196213 |  | 300000000 | 200507 |  | 130
132 | [17 empty] | 132
133 | [17 empty] | 133
134 | [17 empty] | 134
135 | [17 empty] | 135
136 | [17 empty] | 136
137 | [17 empty] | 137
138 | [17 empty] | 138
139 | [17 empty] | 139
140 | [17 empty] | 140
141 | [17 empty] | 141
142 | [17 empty] | 142
143 | [17 empty] | 143
144 | [17 empty] | 144
148 | [17 empty] | 148
149 | [17 empty] | 149
150 | [17 empty] | 150
151 | [17 empty] | 151
152 | [17 empty] | 152
155 | [17 empty] | 155
156 | [17 empty] | 156
157 | [17 empty] | 157
158 | [17 empty] | 158
159 | [17 empty] | 159
160 | [17 empty] | 160
161 | [17 empty] | 161
162 | [17 empty] | 162
163 | [17 empty] | 163
164 | [17 empty] | 164
165 | [17 empty] | 165
166 | [17 empty] | 166
167 | [17 empty] | 167
168 | [17 empty] | 168
169 | [17 empty] | 169
170 | [17 empty] | 170
171 | [17 empty] | 171
172 | [17 empty] | 172
173 | [17 empty] | 173
174 | [17 empty] | 174
175 | [17 empty] | 175
176 | [17 empty] | 176
177 | [17 empty] | 177
178 | [17 empty] | 178
179 | [17 empty] | 179
180 | [17 empty] | 180
181 | [17 empty] | 181
182 | [17 empty] | 182
183 | [17 empty] | 183
184 | [17 empty] | 184
185 | [17 empty] | 185
186 | [17 empty] | 186
187 | [17 empty] | 187
188 | [17 empty] | 188
189 | [17 empty] | 189
190 | [17 empty] | 190
191 | [17 empty] | 191
192 | [17 empty] | 192
193 | [17 empty] | 193
194 | [17 empty] | 194
195 | [17 empty] | 195
196 | [17 empty] | 196
197 | [17 empty] | 197
198 | [17 empty] | 198
199 | [17 empty] | 199
200 | [17 empty] | 200
201 | [17 empty] | 201
202 | [17 empty] | 202
203 | [17 empty] | 203
204 | [17 empty] | 204
205 | [17 empty] | 205
206 | [17 empty] | 206
207 | [17 empty] | 207
208 | [17 empty] | 208
209 | [17 empty] | 209
210 | [17 empty] | 210
211 | [17 empty] | 211
212 | [17 empty] | 212
213 | [17 empty] | 213
214 | [17 empty] | 214
215 | [17 empty] | 215
216 | [17 empty] | 216
217 | [17 empty] | 217
218 | [17 empty] | 218
219 | [17 empty] | 219
220 | [17 empty] | 220
221 | [17 empty] | 221
222 | [17 empty] | 222
223 | [17 empty] | 223
224 | [17 empty] | 224
225 | [17 empty] | 225
226 | [17 empty] | 226
227 | [17 empty] | 227
228 | [17 empty] | 228
229 | [17 empty] | 229
230 | [17 empty] | 230
231 | [17 empty] | 231
232 | [17 empty] | 232
233 | [17 empty] | 233
234 | [17 empty] | 234
235 | [17 empty] | 235
236 | [17 empty] | 236
237 | [17 empty] | 237
238 | [17 empty] | 238
239 | [17 empty] | 239
240 | [17 empty] | 240
241 | [17 empty] | 241
242 | [17 empty] | 242
243 | [17 empty] | 243
244 | [17 empty] | 244
245 | [17 empty] | 245
246 | [17 empty] | 246
247 | [17 empty] | 247
248 | [17 empty] | 248
249 | [17 empty] | 249
250 | [17 empty] | 250
251 | [17 empty] | 251
252 | [17 empty] | 252
253 | [17 empty] | 253
254 | [17 empty] | 254
255 | [17 empty] | 255
256 | [17 empty] | 256
257 | [17 empty] | 257
258 | [17 empty] | 258
259 | [17 empty] | 259
260 | [17 empty] | 260
261 | [17 empty] | 261
262 | [17 empty] | 262
263 | [17 empty] | 263
264 | [17 empty] | 264
265 | [17 empty] | 265
266 | [17 empty] | 266
267 | [17 empty] | 267
268 | [17 empty] | 268
269 | [17 empty] | 269
270 | [17 empty] | 270
271 | [17 empty] | 271
272 | [17 empty] | 272
273 | [17 empty] | 273
274 | [17 empty] | 274
275 | [17 empty] | 275
276 | [17 empty] | 276
277 | [17 empty] | 277
278 | [17 empty] | 278
279 | [17 empty] | 279
280 | [17 empty] | 280
281 | [17 empty] | 281
282 | [17 empty] | 282
283 | [17 empty] | 283
284 | [17 empty] | 284
285 | [17 empty] | 285
286 | [17 empty] | 286
287 | [17 empty] | 287
288 | [17 empty] | 288
289 | [17 empty] | 289
290 | [17 empty] | 290
291 | [17 empty] | 291
292 | [17 empty] | 292
293 | [17 empty] | 293
294 | [17 empty] | 294
295 | [17 empty] | 295
296 | [17 empty] | 296
297 | [17 empty] | 297
298 | [17 empty] | 298
299 | [17 empty] | 299
300 | [17 empty] | 300
95 | 3 | C | 87-5679 | CANX | N/A |  | N/A |  | <=N/A |  | 1418394533 | [6 empty] | 95
96 | 3 | C | 03-1510 | CANX | N/A |  | N/A |  | <=N/A |  | 1418394533 | [6 empty] | 96
97 | 3 | C | 99-1019 | CANX | N/A |  | N/A |  | <=N/A |  | 1418394533 | [6 empty] | 97
98 | 3 | C | 00-1020 | CANX | N/A |  | N/A |  | <=N/A |  | 1418394533 | [6 empty] | 98
99 | 3 | C | 68-4643 | CANX | N/A |  | N/A |  | <=N/A |  | 1418394533 | [6 empty] | 99
100 | 3 | C | 03-1136 | CANX | N/A |  | N/A |  | <=N/A |  | 1418394533 | [6 empty] | 100
101 | 3 | C | 02-1034 | CANX | N/A |  | N/A |  | <=N/A |  | 1418394533 | [6 empty] | 101
145 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | 145
146 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | 146
147 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | 147
153 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | 153
154 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | 154
131 | 5 | 2 | 05-1725 | [14 empty] | 131
Note on C61: B: Base Year, 1: Option Year 1, 2: Option Year 2, 3: Option Year 3 and M: MOA, C: Cancelled
Note on E61: Black Bold: DO#, initial award. Black Normal: DO# accompanying Mod. Red Bold: DO# reserved due to RTA CANX = Project cancelled
Note on F61: Mod #. N/A = initial award
Note on H61: When DO is awarded, you need sort PB tracker data by award date. 1. Go to Menu Bar and click "Data". 2. Select "Sort" 3. Select "Awrd Date". 4. Selcet "Ascending Order". 5. Click "OK"
Cell color changed into "Yellow" is a "Warning" for additional bonding.

## Data_BNJ (hidden)
Database | Ser# | Active | FY | YR | QKKA | DO# | Mod | Title | BLDG | Location | ¥ Rate | AF 9 (¥) | GCE (¥) | Award (¥) | Award ($) | NPI (¥) | NPI ($) | NPI % | PR Date | Awd Date | NTP | CompDate | Final Date | Schedule | Actual | Latest Status or Reason for Modification | B/S | CALT | Warranty | Warranty | Voucher # | Date Paid | Final Accept | Close-Out | Closed out
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Progress Chart Dbase - Automatic Data-in/Data-out for up to 30 Dos
Ser# | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Delivery Order # | 5059 | 5060 | 5064 | 5065 | 5069 | 5070
Proj Site/Bldg # | 1522 | 98 | 1006 | 1500 | Q 114D | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completion | 2005-07-18 | 2005-09-06 | 2005-06-27 | 2005-08-02 | 2005-11-14 | 2005-10-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Progress % | 90% | 6% | 99% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sched'l Progress % | 50% | 6% | 99% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Delivery Order # | 5059 | 5060 | 5064 | 5065 | 5069 | 5070
Project Site / Bldg # | 1522 | 98 | 1006 | 1500 | Q 114D | 948
Completion Date | 2005-07-18 | 2005-09-06 | 2005-06-27 | 2005-08-02 | 2005-11-14 | 2005-10-14
Delivery Order #
Project Site / Bldg #
Completion Date
For Progress Chart | DO# | Mod | Final Date | Final Date
Active DO | >5000 | N/A | = | 0 |  | Pending Award: |  | 0
| < 6 Acitive DO(s), as of | 2026-07-30 | >
PB Tracker Database |  |  | Today | 2026-07-30 | #N/A |  |  |  |  | Log | Tracker | 1 | 2 | 3 | 4 | 5
[7 empty] | Cross-reference |  |  | Enter Date |  |  | PB Balance |  |  | Enter Bond Inc/Dec
YYYMM | YYMMM | AWD | Complete | Active DO Amt | Bond |  | YYYM | YYYMM | < MO End | 2003-01-14 | #N/A |  | 53360000
200303 | '03 Mar | 16544431 | 0 | 16544431 | 53360000 |  | 20031 | 200301 | 2003-02-01 | 2003-04-17 | 2003-04-09 | 7 | 253360000 |  |  | 200000000
200304 | '03 Apr | 45946100 | 3188160 | 59302371 | 253360000 |  | 20032 | 200302 | 2003-03-01 | 2003-07-01 | 2003-06-30 | 35 | 403360000 |  |  | 150000000
200305 | '03 May | 58127614 | 30577585 | 86852400 | 253360000 |  | 20033 | 200303 | 2003-04-01 | 2003-08-26 | 2003-08-26 | 39 | 763360000 |  |  | 360000000
200306 | '03 Jun | 220655384 | 0 | 307507784 | 403360000 |  | 20034 | 200304 | 2003-05-01 | 2003-10-06 | 2003-09-30 | 93 | 874360000 |  |  | 111000000
200307 | '03 Jul | 390506288 | 20076827 | 677937245 | 403360000 |  | 20035 | 200305 | 2003-06-01 | 2004-01-09 | 2003-12-18 | 88 | 763360000 |  |  | -111000000
200308 | '03 Aug | 31174783 | 3783610 | 705328418 | 763360000 |  | 20036 | 200306 | 2003-07-01 | 2004-08-03 | 2004-07-26 | 109 | 403360000 |  |  | -360000000
200309 | '03 Sep | 358344369 | 65327664 | 998345123 | 874360000 |  | 20037 | 200307 | 2003-08-01 | 2005-02-24 | 2005-02-09 | 128 | 300000000 |  |  | -103360000
200310 | '03 Oct | 0 | 78443398 | 919901725 | 874360000 |  | 20038 | 200308 | 2003-09-01
200311 | '03 Nov | 0 | 87396449 | 832505276 | 874360000 |  | 20039 | 200309 | 2003-10-01
200312 | '03 Dec | 957487 | 119379924 | 714082839 | 763360000 |  | 200310 | 200310 | 2003-11-01
200401 | '04 Jan | 0 | 14335900 | 699746939 | 763360000 |  | 200311 | 200311 | 2003-12-01
200402 | '04 Feb | -574490 | 86892325 | 612280124 | 763360000 |  | 200312 | 200312 | 2004-01-01
200403 | '04 Mar | 40208592 | 75700768 | 576787948 | 763360000 |  | 20041 | 200401 | 2004-02-01
200404 | '04 Apr | 26493434 | 0 | 603281382 | 763360000 |  | 20042 | 200402 | 2004-03-01
200405 | '04 May | -4060 | 87218398 | 516058924 | 763360000 |  | 20043 | 200403 | 2004-04-01
200406 | '04 Jun | 961021 | 110388650 | 406631295 | 763360000 |  | 20044 | 200404 | 2004-05-01
200407 | '04 Jul | 7023508 | 132902620 | 280752183 | 403360000 |  | 20045 | 200405 | 2004-06-01
200408 | '04 Aug | 36301976 | 110130585 | 206923574 | 403360000 |  | 20046 | 200406 | 2004-07-01
200409 | '04 Sep | 145004098 | 139767029 | 212160643 | 403360000 |  | 20047 | 200407 | 2004-08-01
200410 | '04 Oct | 0 | 44313248 | 167847395 | 403360000 |  | 20048 | 200408 | 2004-09-01
200411 | '04 Nov | 313034 | 0 | 168160429 | 403360000 |  | 20049 | 200409 | 2004-10-01
200412 | '04 Dec | 14886316 | 5400058 | 177646687 | 403360000 |  | 200410 | 200410 | 2004-11-01
200501 | '05 Jan | 1959369 | 0 | 179606056 | 403360000 |  | 200411 | 200411 | 2004-12-01
200502 | '05 Feb | 2859832 | 0 | 182465888 | 300000000 |  | 200412 | 200412 | 2005-01-01
200503 | '05 Mar | 10143409 | 26328802 | 166280495 | 300000000 |  | 20051 | 200501 | 2005-02-01
200504 | '05 Apr | 0 | 31840935 | 134439560 | 300000000 |  | 20052 | 200502 | 2005-03-01
200505 | '05 May | 0 | 36301976 | 98137584 | 300000000 |  | 20053 | 200503 | 2005-04-01
200506 | '05 Jun | 0 | 10143409 | 87994175 | 300000000 |  | 20054 | 200504 | 2005-05-01
200507 | '05 Jul | 10562038 | 0 | 98556213 | 300000000 |  | 20055 | 200505 | 2005-06-01
200508 | '05 Aug | 0 | 0 | 98556213 | 300000000 |  | 20056 | 200506 | 2005-07-01
200509 | '05 Sep | 0 | 0 | 98556213 | 300000000 |  | 20057 | 200507 | 2005-08-01
200510 | '05 Oct | 0 | 0 | 98556213 | 300000000 |  | 20058 | 200508 | 2005-09-01
200511 | '05 Nov | 0 | 0 | 98556213 | 300000000 |  | 20059 | 200509 | 2005-10-01
200512 | '05 Dec | 0 | 0 | 98556213 | 300000000 |  | 200510 | 200510 | 2005-11-01
200601 | '06 Jan | 0 | 0 | 98556213 | 300000000 |  | 200511 | 200511 | 2005-12-01
200602 | '06 Feb | 0 | 0 | 98556213 | 300000000 |  | 200512 | 200512 | 2006-01-01
200603 | '06 Mar | 0 | 0 | 98556213 | 300000000 |  | 20061 | 200601 | 2006-02-01
200604 | '06 Apr | 0 | 0 | 98556213 | 300000000 |  | 20062 | 200602 | 2006-03-01
200605 | '06 May | 0 | 0 | 98556213 | 300000000 |  | 20063 | 200603 | 2006-04-01
200606 | '06 Jun | 0 | 0 | 98556213 | 300000000 |  | 20064 | 200604 | 2006-05-01
200607 | '06 Jul | 0 | 0 | 98556213 | 300000000 |  | 20065 | 200605 | 2006-06-01
200608 | '06 Aug | 0 | 0 | 98556213 | 300000000 |  | 20066 | 200606 | 2006-07-01
200609 | '06 Sep | 0 | 0 | 98556213 | 300000000 |  | 20067 | 200607 | 2006-08-01
200610 | '06 Oct | 0 | 0 | 98556213 | 300000000 |  | 20068 | 200608 | 2006-09-01
200611 | '06 Nov | 0 | 0 | 98556213 | 300000000 |  | 20069 | 200609 | 2006-10-01
200612 | '06 Dec | 0 | 0 | 98556213 | 300000000 |  | 200610 | 200610 | 2006-11-01
200701 | '07 Jan | 0 | 0 | 98556213 | 300000000 |  | 200611 | 200611 | 2006-12-01
200702 | '07 Feb | 0 | 0 | 98556213 | 300000000 |  | 200612 | 200612 | 2007-01-01
[7 empty] | 20071 | 200701 | 2007-02-01
[7 empty] | 20072 | 200702 | 2007-03-01

## DATA (hidden)
Summary Sheet Information |  |  | Modification # |  | Modification Amount | [6 empty] | Number of Active Projects
YR | DO# | Mod | YR |  | YR | Mod |  | YR | DO# | Mod |  | DO# | Mod | Awd Date | Final Date
B | >0 | N/A | B |  | B | N/A |  | B |  | N/A |  |  | N/A | >0
YR | DO# | Mod | YR |  | YR | Mod |  | YR | DO# | Mod
1 | >0 | N/A | 1 |  | 1 | N/A |  | 1 |  | N/A
YR | DO# | Mod | YR |  | YR | Mod |  | YR | DO# | Mod |  | DO# | Mod | Awd Date | Final Date
2 | >0 | N/A | 2 |  | 2 | N/A |  | 2 |  | N/A |  |  | N/A | >0 | >0
YR | DO# | Mod | YR |  | YR | Mod |  | YR | DO# | Mod
3 | >0 | N/A | 3 |  | 3 | N/A |  | 3 |  | N/A
YR | DO# | Mod | YR |  |  | Mod
B | >0 | N/A | B |  |  | N/A
1 |  |  | 1
2 |  |  | 2
3 |  |  | 3
YR | Mod
B | N/A
YR | Mod | DO# | Award ($) | YR | Mod | DO# | Award ($) |  | DO# | Mod | Closed
B | N/A | >0 | <25000 | B | N/A | >0 | >=25000 |  | >0 | N/A | Done
YR | Mod | DO# | Award ($) | YR | Mod | DO# | Award ($) |  | 51 | 65 | Pending Closeout: |  | 14
1 | N/A | >0 | <25000 | 1 | N/A | >0 | >=25000
YR | Mod | DO# | Award ($) | YR | Mod | DO# | Award ($)
2 | N/A | >0 | <25000 | 2 | N/A | >0 | >=25000
YR | Mod | DO# | Award ($) | YR | Mod | DO# | Award ($)
3 | N/A | >0 | <25000 | 3 | N/A | >0 | >=25000
YR | Mod | Award (¥)
B | N/A | >0
YR | Mod | Award (¥)
1 | N/A | >0
YR | Mod | Award (¥)
2 | N/A | >0
YR | Mod | Award (¥)
3 | N/A | >0
YR | Mod | Award (¥)
B | N/A | >0
1
2
3